## Work and funds disb. schedule
UPDATED WORK AND FUNDS DISBURSEMENT SCHEDULE UNDER THE B.E. CONTRIBUTION
PROJECT I: Supporting women in cross-border trade
|  | 2018-2019* | 2019-2020* | 2020-2021* | 2021-2022* | TOTAL in $,000 Euros
Components/Key outputs
1 | Women CBT trade knowledge and capacity strengthening | 180 | 180 | 180 | N/A | 540
| A training program is deployed to strengthen women CBTers knowledge of key cross-border and export trade policies and procedures | 50 | 30 | 30 | N/A | 110
| ICT for women CBTers is piloted : an SMS plate-form is created for info dissemination to women traders | 50 | 70 | 50 | N/A | 170
| A markets linkages program for CBTers in Gatumba is delivered | 80 | 80 | 100 | N/A | 260
2 | Capacity building of CBTers supporting institutions and systems | 160 | 150 | 150 | NA | 460
| A national cross-border trade strategy is finalized and validated by stakeholders | 30 | 0 | 0 | NA | 30
| CBTers are assisted to form associations/cooperatives/networks and existing ones are strengthened | 100 | 70 | 70 | NA | 240
| A cross-border trade unit including a section on women is established | 20 | 60 | 60 | NA | 140
| A Trade information and support desk for women CBT is operationalized | 10 | 20 | 20 | NA | 50
3 | Social empowerment for women cross-border traders | 60 | 70 | 70 | NA | 200
| Advocacy capacity of CBTers associations strengthened | 30 | 20 | 20 | NA | 70
| Advocacy agenda and policy papers developed | 10 | 10 | 10 | NA | 30
| Sensitiation/dialogue sessions/events on issues of social empowerment of women is supported | 20 | 40 | 40 | NA | 100
| Total direct activities costs | 400 | 400 | 400 | NA | 1200
4 | Program management costs* | 100 | 100 | 100 | NA | 300
Total project I costs |  | 500 | 500 | 500 | NA | 1500
PROCECT II: Supporting women in fisheries
Component/planned outputs |  |  | 2019-2020* | 2020-2021* | 2021-2022* | TOTAL in $,000 Euros
Components/planned outputs
1 | Producer/Trade knowledge and capacity increased | N/A | 290 | 290 | 240 | 820
| Awareness raising on environmental issues along Lake Tanganyika | N/A | 40 | 40 | 20 | 100
| Cost-sharing grants to co-fund investments for improving product handling, storing, packaging and labelling are provided | N/A | 150 | 150 | 120 | 420
| Markets identification and linkages for producers and traders are facilitated | N/A | 100 | 100 | 100 | 300
2 | Capacity of national supporting institutions and systems is built | N/A | 100 | 90 | 90 | 280
| Producers and traders in the fisheries are assisted to form associations/cooperatives/networks and existing ones are strengthened | N/A | 80 | 60 | 60 | 200
| Support provided to the agribusiness chamber and the fisherman associations and logistics to develop joint solutions to export issues | N/A | 20 | 30 | 30 | 80
3 | A PP dialogue to create/maintain an enabling environment for cross/border and export trade in the palm oil and fruits sub-sectors is established and functionning | N/A | 60 | 70 | 70 | 200
| Advocacy capacity of producers/traders associations strengthened | N/A | 20 | 20 | 20 | 60
| Support provided to the Federal Chamber of Commerce to reinforce industry associations advocacy reach | N/A | 20 | 30 | 30 | 80
| policy dialogue sessions on development of the fisheries supported | N/A | 20 | 20 | 20 | 60
| Total total direct activities costs | N/A | 450 | 450 | 400 | 1300
5 | Program management costs* | N/A | 50 | 50 | 100 | 200
| TOTAL PROJECT II COSTS | N/A | 500 | 500 | 500 | 1500
Note: | 2018-2019* indicates the period running from February 1, 2018 to Bebruary 1, 2019
2019-2020* indicates the period running from February 1, 2019 to February 1, 2020
2020-2021* indicates the period running from February 1,2020 to february 1, 2021
2021-2022* indicates the period running from February 1, 2021 to February 1, 2020
Program management costs* include costs for procurement of implementation agencies, baseline studies, and monitoring and evaluation, etc