FEBRUARY 2019

Acronyms	3

1. Intervention at a glance	4

1.1	Intervention form	4

1.2	Budget execution	4

2. Context	5

2.1	General context	5

2.2	Management context: execution modalities	5

2.3	Harmo-context	6

3. Analysis of progress made	7

3.1	Studies	7

3.1.1	Progress of studies	7

3.1.2	Analysis of studies completed	7

3.2	Expertise	7

3.2.1	Progress of expertise	8

3.3	Budget execution	8

3.4	Quality criteria	9

3.5	Risk management	9

4. Steering and Learning	10

4.1	Action Plan	10

4.2	Lessons Learned	10

5Annexes	11

5.1	“Budget versus current (y – m)” Report	11

5.2	Decisions taken by the JLCB and follow-up	11

# Acronyms

| BTC | Belgian Technical Cooperation (old name) |
| --- | --- |
| ENABEL | Belgian Development Agency (new name) |
| IDCP | Indicative Development Cooperation Programme |
| IGA | Income Generation Activities Project |
| JLCB | Joint Local Consultative Body |
| JLPC | Joint Local Partners Committee |
| LED | Local Economic Development |
| LGAs | Local Government Authorities. |
| M&E | Monitoring and Evaluation |
| MAFC | Ministry of Agriculture Food Security & Cooperatives |
| MNRT | Ministry of Natural Resources and Tourism |
| MOFP | Ministry of Finance & Planning |
| NRM | Natural Resources Management |
| PO | Programme Officer |
| PMO-RALG | Prime Minister’s Office Regional Administration & Local Governments |
| PO- RALG | President’s Office Regional Administration & Local Governments |
| SCF | Belgium Tanzanian Study and Consultancy Fund |
| TARURA | Tanzania Rural & Urbans Roads Agency |
| TOR | Terms of Reference |

# Intervention at a glance

## Intervention form

| Intervention name | Belgian Tanzanian Study and Consultancy Fund |
| --- | --- |
| Intervention Code | 01005 |
| Location | Tanzania |
| Budget | 3.620.000 Euro + 260.42 = 3,880,420.00 Euro |
| Partner Institution | Ministry of Finance and Planning |
| Date of implementation Agreement | 06/12/2001 |
| Duration (months) | 12 years + 2 +2 + 2 +2 = 20 years |
| SA end date | October 2021. |
| Objective | Financing studies and consultancies in the priority sectors, preparatory studies in the context of Belgian Tanzanian cooperation programme, and implementation of the Paris Declaration. |

## Budget execution

| Total Budget | Total exp | Exp 2018 | Disbursement rate | Committed Balance | Uncommitted Balance |
| --- | --- | --- | --- | --- | --- |
| 3,880,420 | 2,721,232.86 | 13,302.86 |  | 70,000.00 | 1,089,187.14 |

| National execution official James Kamomonga | Enabel execution official Cranmer Chiduo |
| --- | --- |

# Context

## General context

Tanzania continued experiencing a new leadership style from President John Magufuli of fighting corruption, embezzlement of public funds, tax evasion, forgeries and laziness. The slogan of “Hapa kazi tu” in Kiswahili meaning Business unusual inspired the way of conducting business in the public sector.

Moreover, the decision to shift the capital to Dodoma had an effect on communication between development partner’s offices still in Dar es Salaam and the ministries officials who have already shifted to the new capital.

In 2018 the ideals proclaimed in 2016 continued to prevail. The restrictions on local and foreign travels by government officials, holding of meetings, workshops and seminars in government buildings, no sitting allowances have remained the order of the day.

BTC changed its name to be in line with its revised mandate. The new name as from 1st January 2018 has been Enabel denoting the Belgium’s mission of enabling partners to manage better their development endevours.

## Management context: execution modalities

There has been very little implementation in 2018. One study on a Feasibility study for construction of stone paved roads in Kigoma was approved late in 2017, consultant selection was done in Q1 and Q2 2018. Consultant selection was done by the use of special tender committee set for that particular purpose, in accordance to the new SCF guidelines.

Contract was drafted for approval by Fund Director at MoFP but was not signed due to lack of clarity on mandates of the new commissioner for external finance in the new government setup.

Generally the execution modalities is APPROPRIATE.

## Harmo-context

## The study on stone paved roads is being implemented in Kigoma Ujiji municipal council. This is the only council in Kigoma region not benefitting from the 3 Belgian funded projects.

# Analysis of Progress

## Studies

### Progress of studies

| SN | Title of Study/Consultancy | ID No. | Amount Approved (Euro) | A | B | C | D | Comments (only if the value is C or D) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | KMC TARURA | 64 | 70,000 |  | X |  |  |  |
| TOTALS | 70,000 |  |  |  |  |  |

A:	completed in year N

B	ongoing

C 	in preperatory phase: preperation going as planned (writing ToR, procurement procedure, etc.)

D 	planned but delayed

### Analysis of studies completed

| Title of Study: | (No study was completed in 2018) |
| --- | --- |
| Describe, in a few sentences, for who the study was organised, and what it was about |  |
| Have the studies been used as intended? |  |
| To what did the study contribute? |  |
| Issues that arose, influencing factors (positive or negative)? Unexpected results (positive or negative)? How did they impact the study or the use of the study? |  |

## Expertise

### Progress of expertise

| Progress of expertise | A | B | C | D | Comments |
| --- | --- | --- | --- | --- | --- |

## Budget execution

In 2018 only one study approved in 2017 was being implemented. Proposals from consultants were solicited by public tender. The process was stuck at the stage of issuing contract. To date no funds have been paid to the consultants.

## Quality criteria

| Criteria | Score |
| --- | --- |
| Relevance | A |
| Efficiency | B |
| Effectiveness | A |

## Risk management

The major risks identified are described below:

- Delays in selection of consultant: The old system of using Tanzania public procurement procedures has been replaced by the use of Special Tender Committees.

- Delays in supporting proposals at application stage or after approval stage due to BTC SPO being too occupied by the need to support other ongoing studies or projects. It was proposed that a full-time projects assistant be recruited to assist in the needed follow-ups to the studies. The situation has changed that the projects being followed up by SPO has decreased from 5 down to 3. All the 3 are in Kigoma. In most cases supervision is done for all at the same time.

- Inability to make effective monitoring the performance of studies: To mitigate the risk all contract will be made in such a way periodic session for feed backs are integral part of the contracts. This has happened in all new studies. Most studies are broken into several tranches between 4 and 7. Reports are expected before a subsequent tranche is disbursed

- Poor financial reporting is a risk because most consultants employed who are well skilled, available and affordable are not backed by sufficient financial management system within their organisations. Mostly these consultants are hired to deliver an output without a requirement for stringent reporting.

To mitigate the risk, the Fund has included as an annex to the contracts detailed instructions on requirements for financial reporting.

- In 2017, 3 studies were completed, 1 was in closure process and only 1 study was approved. The risk foreseen is that the SCF would have very little activity (dormant) for most part of 2018. This could be discussed further during JLPCs 2018. The result was indeed lack of activities in 2018 and no JLPC was held in 2018.

All the above listed risks and its management identified in 2017 were managed in 2018.

# Steering and Learning

## Action Plan

SCF will endevour to create more awareness and support institutions in the priority sectors of DCP to  utilise the facility in improving efficiency in their institutions. SCF will continue to support institutions to develop proposals that are in line with the objectives of this Fund.

Now with the agreed use of Special Tender Committees, SCF was able to recruit a consultant withing short time after approval of proposal.

Payment to studies by Mpesa system from  Enabel directly to workshop participants has eased handling of logistics and improved transparence. This has reduced the budden of accounting for expenditures by the consultats. This system was applied during tender evaluation.

A standard for reporting would improve the quality of final reports for convenience in sharing extensively.

A anticipated revision of the procedures manual agreed in JLPC of September 2015 has not been done in 2018 for lack of suggestions for improvement.

## Lessons Learned

| Lessons learned | Target audience |
| --- | --- |
| Description of the lesson learned. | The audience that may be interested in the lesson learned. |
| Staff turnover at the Ministry of Finance has resulted into a standstill in contract approval by MoFP. The new commissioner (CEF) had no clear mandates on the roles of a Fund director. Elaborative introduction of new staff in case of turnover will be made to avoid ambiguities. | JLPC |
| Payment by Mpesa system from Enabel direct to workshop participants has eased handling of logistics and improved transparence and accountability. This has reduced the budden of accounting for expenditures by the consultats. | JLPC |
| Single sourcing for consultants should be explicitly motivated, justified. Otherwise consultants selection process, as much as possible should be competetive. | MOFP & Enabel |

# Annexes

## “Budget versus Current (yn-1) Report (in Euros)

| SN | Title of Study/Consultancy | ID No. | Amount approved | Amount actual spent |
| --- | --- | --- | --- | --- |
|  | KMC TARURA | 64 | 70,000 | 0 |
| Totals | 70,000 | 0 |

## Decisions taken by JLCB and Follow-up

- Strategic decision:	No JLPC could be held in 2018 hence no decisions or followup.

Period of Identification:

Action:

# Footnotes

Name and Signature

Name and Signature

A:	Expertise completed in year N

B	Expertise ongoing

C 	Expertise in preperatory phase: preperation going as planned (writing ToR, procurement procedure, etc.)

D 	Expertise planned but delayed

# Text boxes

ANNUAL REPORT 2018

STUDY & CONSULTANCY FUND

TAN 01005