Water and Sanitation Kigoma Region Project

(WASKIRP)

aNNUAL RESULTS REPORT 2018

TAN 1403211

Table of Contents

Acronyms	4

1	Intervention at a glance (max. 2 pages)	5

1.1	Project form	5

1.2	Project performance	6

1.3	Budget execution	6

1.4	Summary	6

2	Analysis of the intervention	7

2.1	Context	7

2.1.1	General context	7

2.1.2	Institutional context	7

2.1.3	Management context: execution modalities	8

2.1.4	Harmo-context	8

2.2	Outcome	9

2.2.1	Analysis of progress made	9

2.2.2	Risk management	12

2.2.3	Potential Impact	17

2.2.4	Quality criteria	17

2.3	Output 1	20

2.3.1	Analysis of progress made	20

2.3.2	Budget execution	22

2.3.3	Quality criteria	22

2.4	Output 2	23

2.4.1	Analysis of progress made	23

2.4.2	Budget execution	24

2.4.3	Quality criteria	24

2.5	Output 3	25

2.5.1	Analysis of progress made	25

2.5.2	Budget execution	26

2.5.3	Quality criteria	26

3	Transversal Themes	27

3.1	Gender	27

3.2	Environment	27

3.3	Other	27

4	Steering and Learning	28

4.1	Action Plan	28

4.2	Lessons Learned	28

5	Annexes	30

5.1	Original Logical framework	30

5.2	Updated Logical framework	33

5.3	MoRe Results at a glance	33

5.4	“Budget versus current (y – m)” Report	33

5.5	Resources	33

5.6	Decisions taken by the JLPC and follow-up	34

# Acronyms

| BTC | Belgian Development Cooperation |
| --- | --- |
| DP | Distribution point (equivalent to WP Water Point) |
| DRC | Danish Refugee Council |
| DWE | District Water Engineer |
| ENABEL | Belgian Development Agency |
| HWTS | Household Water Treatment and Safe Storage |
| IFO | International Finance Officer |
| ITA | International Technical Assistant |
| JLPC | Joint Local Partners Committee |
| LGA | Local Government Authorities |
| M&E | Monitoring and Evaluation |
| MoWI | Ministry of Water and Irrigation |
| N/A | Not Applicable |
| NRM4LED | Natural Resource Management for Local Economic Development |
| PIU | Project Implementation Unit |
| RR | Resident Representative |
| RS | Regional Secretariat |
| SAKIRP | Sustainable Agriculture Kigoma Region Project |
| TCRA | Tanzanian Christian Relief Agency |
| TFF | Technical and Financial File |
| ToR | Terms of Reference |
| TWE | Town Water Engineer |
| UNHCR | United Nations High Commissioner for Refugees |
| WASH | Water, Sanitation and Hygiene |
| WP | Water Point (equivalent to DP Distribution Point) |

# Intervention at a glance

## Project form

| Project name | Water and Sanitation Kigoma Region Project (WASKIRP) |
| --- | --- |
| Project Code | TAN1403211 |
| Location | Kigoma Region (rural) |
| Budget | €8 million (Belgian) + €800,000 (Partner) |
| Partner Institution | Ministry of Water and Irrigation (MoWI) |
| Date of implementation Agreement | July 11, 2017 |
| Duration (months) | 60 |
| Target groups | The final direct beneficiaries of the project are households of the six areas covered by rehabilitation / extension of water supplies. These multi-village schemes will serve 26 villages in total which represents 200,000 direct beneficiaries by 2028. The hygiene promotion campaign will mainly focus on communities living in the villages targeted by the project. A large number of people will benefit from broader media, such as radio messages. Terms of Reference of the hygiene promotion campaign will specify the different groups to be targeted. Key stakeholders are also part of the beneficiaries from this project as they are fully integrated in capacity development activities and intervene as intermediates in output delivery. |
| Impact | To contribute towards equitable development and poverty reduction among Kigoma rural communities through improved access to safe and clean water supply and sanitation services4 |
| Outcome | Improved access to safe drinking water sources |
|  | Improved Hygiene practices |
| Outputs | A1. Community Owned Water Supply Organisations are managing rural water supply schemes in a sustainable way |
|  | A2. 200,000 inhabitants have access to safe drinking water that reduces water related burden through rehabilitation and extension of existing assets |
|  | A3 Households have improved their hygiene practices towards water collection, transport, storage and use |

## Project performance self-assessment

Output 1: Community Owned Water Supply Organisations are managing rural water supply schemes in a sustainable way

Contrary to the assumptions that informed the design of the project, the assessment carried out by the project show that COWSOs are non-existent in the project area.  This explains, in part, the reason most of the schemes are malfunctioning and others are no longer operational.  The state of affairs regarding these community-based water supply management structures affected the plans that the project had to carry out a baseline study and to develop its capacity development plan. The COWSO capacity planning was therefore postponed until the project established, which schemes it would make its investment into.

Building the capacity of the community-based water supply management structure is not only aligning the project plans to the rural water supply policies of the Tanzanian government, but also remains relevant and most effective way of ensuring that the schemes that the project will redevelop are sustainable. This intervention therefore remains one of its highest priorities in the coming calendar and financial year.

Output 2: Rehabilitation and extension of water supply infrastructure to 200,000 people

Like the output above, the real situation on the ground does not match with the conditions established at the design of the project in the Specific Agreement.  The project’s own assessment reveal that the situation is mainly due to depleting surface water resources, aging and or existence of old infrastructure and increased population.  The project further carried out preliminary studies, reduced the number of beneficiary villages and schemes, and drew up more realistic cost estimates which were presented to the Steering Committee for approval.  The new proposals were approved and now the project is preparing Tender Specifications to engage consultants to undertake design studies, hydrogeological surveys to inform best investment options that the project will take.

The reality on the ground shows that supplying enough quantities of quality water is a real need in the targeted areas.  The project is therefore highly relevant to the socio-economic development of the people in the targeted villages.  The re-targeting that the project embarked on is meant to increase its effectiveness in utilization of the available resources.

Output 3: Households have improved their hygiene practices towards water collection, transport, storage and use

As this output is related to water supply infrastructure rehabilitation and development, no activities were undertaken towards achieving this result objective. The project will target only the communities that are targeted for the water supply interventions.  Now that the new sites have been established, the project has developed terms of reference for consultants to carry out studies on knowledge attitudes and practices in sanitation and hygiene with focus on water collection, transport, storage and use.

## Project management changes

The project management turnover affected the pace of the project.  The first International Technical Assistant of the project resigned.  An interim project manager was identified before a new ITA was recruited.  Now the project is gathering pace and sooner than later, substantial progress towards results will be achieved.

## Budget execution

Following the unfolding of events outlined above, the execution of the project budget is as below.

| Total Budget € | Expenditure year 2017 | Expenditure year 2018 € | Balance € | Total Disbursement rate 2018 against total |
| --- | --- | --- | --- | --- |
| 8,000,000 | 107,795 | 297,067.77 | 7,595,137 | 5.84% |

Please note that with a substantial amount of the financial resources allocated to rehabilitation and construction of infrastructure, the project expects to realize a higher rate of expenditure once the works commence.

## Summary

Five key points from this report to remember:

Assessment and verification made on targeted water schemes indicate that stated statements in TFF on water status of targeted schemes is contrary to the reality on the ground. This state of affairs required to make amendments to the project.

Surface water sources in the project areas have declined which necessitate identification of new sources and verification of their capacities before investments are made

Since all the outputs are interlinked, delay in establishing the sites for the water supply infrastructure rehabilitation and development affected other objectives of the project

# Analysis of the intervention

## Context

### General context

The project is completely anchored in current Government Water Policies and Strategies and will support the attainment of SDG 6 in Tanzania (policies and strategies will not be mentioned here again, as they are comprehensively detailed in the TFF and available for the general public).

Two facts that could have an impact in project implementation should be highlighted, as the project it is still at its start-up phase, project adaptation should be easy:

- The MoWI is currently discussing about a new strategy to be established in order to ensure rural water schemes sustainability: up to now the burden of management and sustainability is completely the responsibility of the Water Committees or COWSOs and the district councils. However, the approach has proved have low capacity in terms of; finance, technical and managerial skills. Most of the failure of the scheme National wide is attributed to both inadequate support or inadequate management. Enabel WASKIRP roles will be; to establish and strengthen the COWSOS and to create long tem sustainability of OM capacity

- Initial assessment of the projects indicates that the project will have to be most of the surface water sources are declining due to a number of factor of which most is the anthropogenicAfter visiting all targeted schemes intakes, it has been stated that in most cases surface water is not a reliable water source anymore (due to several factors) as water streams and springs from where the targeted schemes take the water, have either completely dried up or are drying. In all cases, there is a high seasonal variability. It has been also stated that in some cases the scheme needs to be rebuilt completely as old elements are missing or need to be rebuilt. This could have an impact on total costs of the hardware component.

### Institutional context

The institutional anchorage of the intervention remains highly appropriate as it involves all necessary stakeholders having an impact in water supply, water schemes’ management and water resources management. The set up is valid and it proved to be useful during 2018. Both, the Regional Secretariat of the Kigoma Region under the Regional Administrative Secretary (RAS) and the District Councils played their roles in ensuring that the preparatory stage of the intervention was successful. The two facilitated a smooth assessment of the water status throughout the 26 villages and in all further planning process of prioritization for the implementation of the intervention. Putting in mind that the Districts will be accountable for deliverables from the interventions- Enabel ensured that fully involvement of the two in decision making on the intervention began at the early stage of the assessment of the water status of the targeted schemes. More stakeholders involved in verification of water status were the Lake Tanganyika Basin & The Zonal Water Quality Laboratory who conducted flow measurement and water quality respectively. The two worked on11 water sources in the targeted area. WASKIRP will extend collaboration with the two entities as per legislations guiding this intervention and as per Enabel’s guiding principles observed in implementing public works worldwide.

Lake Tanganyika Basin Water Board in an institution responsible for management of water resources in the entire Basin, hence it would be of utmost important to work with it to avoid negative effects on water allocations, to boost catchment protection activities, to fix safe water yields and to monitor the trend of water resources with a focus on targeted scheme sustainability.

### Management context: execution modalities

Up to now, current execution modalities (as described in WASKIRP TFF) seem to be very appropriate. Experience earned during the year (2018) indicate that the designed management context will guide the project to achieve its planned objectives.

### Harmo-context

During 2018 the harmonization with other actors was established and strengthened differently at different levels.:

- Internally the harmonization was strengthened between WASKIRP and other sister Enabel projects of SAKIRP and NRM4LED. WASKIRP and SAKIRP shared administrative support services and their collaboration were strengthened through this set up. Transport were as well shared among the 3 projects wherever a need arose. More collaboration was evidenced through few coordination meetings between Project Managers.

- Collaboration with External actors working in WASH sector in the Kigoma Region was not much a success despite effort made in consulting them. Few of the consulted included; TCRS, Oxfam, DRC, Water Missions, Flemish Red Cross and UNHCR most of these work on refugee program in refugee camps. However, few of them work in host communities in villages surrounding the Refugee Camps.  A particular case occurred at Zeze village in Kasulu Rural district were Enabel withdrew its assistance after finding out that Water Mission had stated to work in the village on Water Supply even without its knowledge

- Harmonization with main partner actors was implemented at different levels i.e. during assessment of the actual water situation of the schemes through 30 Mission visits to the targeted villages/water schemes where Enabel team had meetings with; various people and institutions which included; RAS, District Commissioners (DC), District Executive Directors (DED), District Water Engineers (DWEs), Civic Leaders Village Governments, Water Committee Leaders and the Local Communities. More harmonization was achieved through higher-level decision-making meetings of the WASKIRP through; 2 Project Implementation Unit meetings (PIU that involved; RAS, DEDs DWEs & Lake Tanganyika Basin Water Board. And 2 JLPC which involved -MoW, MoF, PMO-RALG and the Kigoma -RAS

## Outcome

Give an overview of the likely achievement of the Outcome (i.e. outcome) and the dynamics surrounding the Outcome (see figure below).

The project aims to reach 200,000 beneficiaries with reliable supply of clean and safe water. Access to enough quantities of safe water, in line with SDG 6, will improve living conditions of beneficiaries because:

- Times needed to fetch water will be reduced (in most cases both, women and children are the ones in charge of this task). Such time savings can be used for many other productive activities like going to school, allocation of more time on income generating activities.

- The burden of waterborne diseases will be reduced. This will be ensured also through better hygiene practices.

- The availability of safe drinking water as a social commodity will enhance new economic initiatives.

- Public buildings will provide a safer environment for their users (schools, health centres, markets, etc.).

- Water services managed in a sustainable way will be more reliable, will enhance women empowerment and will contribute to environment preservation.

### Analysis of progress made

|  | Outcome: To increase access to safe/clean water and sanitation services and reduce burden related to water & sanitation amongst communities in Kigoma region, especially women and youths, and use the water as social economic commodity through sustainable interventions on water supply and hygiene practices |
| --- | --- |
| Indicators | Baseline value | Progress year N-1 | Progress year N2 | Target year N3 | Target year N4 | End Target | Comments |
| Preliminary indicator: Population of the project area | 197,773 | N/A yet | N/A yet |  |  | 223,762 | Baseline not done yet, values taken from TFF |
| Preliminary indicator: Population with adequate access | 76,448 | N/A yet | N/A yet |  |  | 200,000 | Baseline not done yet, values taken from TFF |
| Preliminary indicator: Access to safe drinking water | 40% | N/A yet | N/A yet |  |  | 90% | Baseline not done yet, values taken from TFF |
| Preliminary indicator: # of public distribution points (DP) | 551 | N/A yet | N/A yet |  |  | 900 | Baseline not done yet, values taken from TFF |
| Preliminary indicator: DP functionality | 55% | N/A yet | N/A yet |  |  | 90% | Baseline not done yet, values taken from TFF |
| Preliminary indicator: # people per functional DP | 804 | N/A yet | N/A yet |  |  | 250 | Baseline not done yet, values taken from TFF |
| Preliminary indicator: # of private connections | To be defined | N/A yet | N/A yet |  |  | to be defined | Baseline not done yet, values taken from TFF |
| Water borne disease statistics | To be defined | N/A yet | N/A yet |  |  | Decreased with minimum 20% | Baseline not done yet, values taken from TFF. |
| Quality of service to users (based on a number of performance indicators: number of days with intermittent supply, tariffs, etc…) | To be defined | N/A yet | N/A yet |  |  | To be defined | Baseline not done yet |
| Number of COWSOs with O&M plans | To be defined | N/A yet | N/A |  |  | Minimum 75% of COWSOs have a O&M plans | Baseline not done yet |
| COWSOs have a sound accounting system | To be defined | N/A yet | NA |  |  | Minimum 85% of COWSOs have a sound accounting system | Baseline not done yet |
| Water points functionality | To be defined | N/A yet | N/A yet |  |  | Minimum 20% more WPs are functional. | Baseline not done yet. This indicator can enter into conflict with the preliminary indicator “DP functionality” because of different targets |
| Water quality complying with standards | To be defined | N/A yet | N/A yet |  |  | 50 % increase of existing WP which comply with standards. | Baseline not done yet |
| Effective protection and sustainable management of water catchments (water permits, physical protection, users’ conflicts…) | To be defined | N/A yet | N/A yet |  |  | 75% of installed water points are protected and sustainably managed | Baseline not done yet |
| Knowledge, attitude and practices (KAP) related to hygiene (during collection, transport, storage and use – example handwashing) | To be defined | N/A yet | N/A yet |  |  | A minimum increase with: 50% for K. 40% for A 30% for P |  |
|  | Analysis of progress made towards outcome: |
| Relation between outputs and the Outcome. (How) Are outputs (still) contributing to the achievement of the outcome: |  | N/A yet because the project is still in its start-up phase |
| Progress made towards the achievement of the outcome (on the basis of indicators): |  | N/A yet because the project is still in its start-up phase |
| Issues that arose, influencing factors (positive or negative): |  | N/A yet because the project is still in its start-up phase |
| Unexpected results: |  | N/A yet because the project is still in its start-up phase |

### Risk management

Please note that as the baseline has not been accomplished yet, the risks analysis presented below has been extracted from the TFF.

| Risk Identification | Risk analysis | Risk Treatment | Follow-up of risks |
| --- | --- | --- | --- |
| Description of Risk | Period of identification | Risk category | Probability | Potential Impact | Total | Action(s) | Resp. | Deadline | Progress | Status |
| Poor procurement and contract management | TFF | Implementation risk | M | H | H | Ensure quality control of tender documents technical specifications | PIU | October 2019 |  | In progress |
|  |  |  |  |  |  | Set appropriate contract management measures at regional, LGA and local level all along the process | PIU – RR | October 2019 |  | In progress |
|  |  |  |  |  |  | Recruit qualified personnel in charge of procurement at project level | PIU – RR - IFO | June 2019 | Qualified personnel in charge of procurement has been recruited | Resolved but continue monitoring |
| Private sector capacity for design studies, works and supervision | TFF | Implementation risk | M | H | H | Optimize procurement procedures, such as prequalification to avoid least qualified companies to bid | PIU - IFO |  | The advice is being observed in the process | Ongoing |
| Rehabilitation and extension final costs estimates from study phase above available budget | TFF | Implementation risk | M | H | H | Clear priority criteria for budget allocation to be established at study phase | PIU – IFO |  | More criteria established in additional to those in TFF. A cost estimate has been made. Intervention has been scaled down from 26 to 15 villages to match with the available budget | Resolved |
| Capacity to mobilize Non- State Actors (for instance in the hygiene promotion component) | TFF | Implementation risk | M | M | M | Conduct a NGO mapping and ensure proper dissemination of the calls | PIU | June 2019 |  | New |
| Insufficient staffing of DWEs offices | TFF | Implementation risk | M | M | M | Sufficient project staff assigned in the weakest Districts (newly established Unviza, Buhigwe & Kakonko) and deployment of project extension workers in each District; contract management of design studies centralized at RS level for all networks | PIU | June 2019 |  | New |
| Delays in implementation caused by the geographical location of Kigoma | TFF | Implementation risk | M | M | M | Realistic planning for activities and supplies | PIU |  | Trying to be as more realistic as much possible in our planning | In Progress |
| Limited working window due to extended rainy season of the region | TFF | Implementation risk | M | M | H | Realistic planning for activities - especially on works | PIU |  | Trying to be as more realistic as much possible in our planning | In Progress |
| Neglect of the importance of the gender dimension activities | TFF | Implementation risk | M | M | M | Top-down accountability for integrating gender at all phases of the programme and at all levels of the PIU. | PIU |  | Gender integration is a priority in WASKIRP planning, despite recruiting female staff in supporting staff an additional female SE has been recruited | In Progress |
| Discrimination of vulnerable populations | TFF | Implementation risk | M | M | M | Continuous awareness raising among all stakeholders about the needs and rights of stigmatized populations such as orphans and vulnerable children, people with a disability and PLHIV. | PIU |  | Awareness on the issues is included in our plans | In Progress |
| Delays of implementation at District level linked to administrative and technical bottlenecks | TFF | Management risks | M | M | M | Provide technical and administrative assistance to Districts to influence bottlenecks, calling on their accountability and on the support through SC. | PIU | Dec 2019 |  | Planned |
| Districts not sufficiently involved in planning and budgeting resulting on poor ownership and coordination of overall activities | TFF | Management risks | M | M | M | Ensure co responsibility of the project and coordination at LGA level by DWEs focal points | PIU |  | Districts are involved in all planning process through PIUs technical meetings | In Progress |
| Delays in contracting service providers due to bureaucratic procedures at region and district for procurement and tendering | TFF | Management risks | M | M | M | Centralize procurement of service contracts as much as possible, but keep a close eye on performance-based payments. | PIU |  |  | Resolved |
| Delays in approval channels of technical matters by chancellors | TFF | Management risks | M | M | M | Increase communication channels and technics to sensitize decision makers | PIU | Dec 2019 |  | Planned |
| Lack of capabilities in administration and procurement of the PIU | TFF | Effectiveness risks | M | M | M | Strong finance and administrative project personnel (shared international and senior finance and administration personnel with SAKiRP and NRM-LED) | HR |  | Required staff are available | Resolved |
| Resistance to collaborate within and between different sections of RS and LGA’s. | TFF | Effectiveness risks | M | L | L | Diversified capacity development technics; ensure permanent presence at LGAs and RS levels | PIU | Dec 2019 | Capacity Development is included in the WASKIRP intervention | Planned |
| Resistance to change | TFF | Effectiveness risks | H | M | H | Address in a progressive way (step by step) service-oriented mind shift, through awareness-raising campaigns, trainings, extension work (for both women and men). | PIU | Dec 2019 |  | Planned |
| Tariffs are not set according to a cost recovery approach | TFF | Sustainability risks | H | H | VH | Develop business plans for COWSO and make these plans a precondition for investments | PIU | Dec 2019 |  | Planned |
| Opposition between community groups / villages | TFF | Sustainability risks | M | H | H | When possible, adapt design to specific cases, such as one water source serving two distinct/villages populations unwilling to cooperate | PIU | Dec 2019 | To be addressed during establishment and strengthening of COWSO | Planned |
|  |  |  |  |  |  | Introduce mediation techniques for conflict resolution at LGAs level | PIU | Dec 2019 |  |  |
|  |  |  |  |  |  | Introduce formal agreements between parties | PIU | Dec 2019 |  |  |
| Water sources drying up or being polluted | TFF | Sustainability risks | H | H | VH | Proper assessment of water sources at design stage before investment | PIU | Dec 2019 | Preliminary Assessment done. Flow measurement conducted made, pumping test conducted, Test drilling has been planned. Prior design study and construction | Resolved |
|  |  |  |  |  |  | Protection or catchments and sensitization of water catchment users | PIU | Dec 2019 | Hot sports have been identified plan for catchment conservation and protection is being made | Planned |
| Continuation of extension work after completion of the project | TFF | Sustainability risks | M | M | M | Develop an exit strategy plan with LGAs for extension workers financed by the project | PIU | July 2020 | Scheduled to be implemented in the last 6 months of the project | Planned |
| Understaffed COWSOs. High turnover of trained COWSO staff | TFF | Sustainability risks | M | L | L | Ensure financial sustainability of COWSOs through capacity development activities (to be treated as a priority from the onset of the intervention) | PIU |  | There’s no active COWSO existing in the project area | Establishment and strengthening process is on the way |
| Ineffective control of financial information at District and Regional level and questionable reliability and inconsistency in report data. | TFF | Fiduciary risks | M | H | H | Prepare Project Implementation Manual (PIM) and Administration and Finance Manual (AFM) early and provide orientation and training and hands on guidance of its use. | PIU - IFO |  | The documents have been prepared | Resolved |
|  |  |  |  |  |  | Provide administrative backup from PIU to districts to help improve quality of reporting | PIU - IFO |  | Planned to be executed in different areas | In progress |
|  |  |  |  |  |  | Centralize key procurement at project finance and tender support unit. | PIU - IFO |  | The system is centralized | Centralized |
|  |  |  |  |  |  | Organize regular financial audits (internal and external) and deal with issues through management reports. | PIU - IFO | 31 Dec 2019 |  | Planned |

### Potential Impact

Once the outcome (access to safe and clean water) is reached, the potential impact (contribute towards equitable development and poverty reduction among Kigoma communities) will be straight forward: there is good evidence that all water, sanitation and hygiene (WASH) investments can have significant health, economic and development benefits and provide excellent value for money, for every $1 invested in water and sanitation, an average of at least $4 is returned in increased productivity (G. Hutton, Global costs and benefits of drinking-water supply and sanitation interventions to reach the MDG target and universal coverage, World Health Organization, Geneva, 2012, p. 4. :

http://www.who.int/water_sanitation_health/publications/2012/globalcosts.pdf )

### Quality criteria match

| 1. RELEVANCE: The degree to which the intervention is in line with local and national policies and priorities as well as with the expectations of the beneficiaries |
| --- |
| In order to calculate the total score for this Q-criterion, proceed as follows: ‘At least one ‘A’, no ‘C’ or ‘D’ = A; Two times ‘B’ = B; At least one ‘C’, no ‘D’= C; at least one ‘D’ = D |
| 1.1 What is the present level of relevance of the project? |
|  | A | Clearly still embedded in national policies and Belgian strategy, responds to aid effectiveness commitments, highly relevant to needs of target group. |
|  | B | Still fits well in national policies and Belgian strategy (without always being explicit), reasonably compatible with aid effectiveness commitments, relevant to target group’s needs. |
|  | C | Some issues regarding consistency with national policies and Belgian strategy, aid effectiveness or relevance. |
|  | D | Contradictions with national policies and Belgian strategy, aid efficiency commitments; relevance to needs is questionable. Major adaptations needed. |
| 1.2 As presently designed, is the intervention logic still holding true? |
|  | A | Clear and well-structured intervention logic; feasible and consistent vertical logic of objectives; adequate indicators; Risks and Assumptions clearly identified and managed; exit strategy in place (if applicable). |
|  | B | Adequate intervention logic although it might need some improvements regarding hierarchy of objectives, indicators, Risk and Assumptions. |
|  | C | Problems with intervention logic may affect performance of project and capacity to monitor and evaluate progress; improvements necessary. |
|  | D | Intervention logic is faulty and requires major revision for the project to have a chance of success. |

| 2. EFFICIENCY OF IMPLEMENTATION TO DATE: Degree to which the resources of the intervention (funds, expertise, time, etc.) have been converted into results in an economical way (assessment for the whole of the intervention) |
| --- |
| In order to calculate the total score for this Q-criterion, proceed as follows: ‘At least one ‘A’, no ‘C’ or ‘D’ = A; Two times ‘B’ = B; At least one ‘C’, no ‘D’= C; at least one ‘D’ = D |
| 2.1 How well are inputs (financial, HR, goods & equipment) managed? |
|  | A | All inputs are available on time and within budget. |
|  | B | Most inputs are available in reasonable time and do not require substantial budget adjustments. However there is room for improvement. |
|  | C | Availability and usage of inputs face problems, which need to be addressed; otherwise results may be at risk. |
|  | D | Availability and management of inputs have serious deficiencies, which threaten the achievement of results. Substantial change is needed. |
| 2.2 How well are outputs managed? |
|  | A | All outputs have been and most likely will be delivered as scheduled with good quality contributing to outcomes as planned. |
|  | B | Output delivery is and will most likely be according to plan, but there is room for improvement in terms of quality, coverage and timing. |
|  | C | Some output are/will be not delivered on time or with good quality. Adjustments are necessary. |
|  | D | Quality and delivery of outputs has and most likely will have serious deficiencies. Major adjustments are needed to ensure that at least the key outputs are delivered on time. |

| 3. EFFECTIVENESS TO DATE: Degree to which the outcome (Specific Objective) is achieved as planned at the end of year N |
| --- |
| In order to calculate the total score for this Q-criterion, proceed as follows: ‘At least one ‘A’, no ‘C’ or ‘D’ = A; Two times ‘B’ = B; At least one ‘C’, no ‘D’= C; at least one ‘D’ = D |
| 3.1 As presently implemented what is the likelihood of the outcome to be achieved? |
|  | A | Full achievement of the outcome is likely in terms of quality and coverage. Negative effects (if any) have been mitigated. |
|  | B | Outcome will be achieved with minor limitations; negative effects (if any) have not caused much harm. |
|  | C | Outcome will be achieved only partially among others because of negative effects to which management was not able to fully adapt. Corrective measures have to be taken to improve ability to achieve outcome. |
|  | D | Project will not achieve its outcome unless major, fundamental measures are taken. |
| 3.2 Are activities and outputs adapted based on the achieved results in order to the outcome (Specific Objective)? |
|  | A | The project is successful in adapting its strategies / activities and outputs to changing external conditions in order to achieve the outcome. Risks and assumptions are managed in a proactive manner. |
|  | B | The project is relatively successful in adapting its strategies to changing external conditions in order to achieve its outcome. Risks management is rather passive. |
|  | C | The project has not entirely succeeded in adapting its strategies to changing external conditions in a timely or adequate manner. Risk management has been rather static. An important change in strategies is necessary in order to ensure the project can achieve its outcome. |
|  | D | The project has failed to respond to changing external conditions, risks were insufficiently managed. Major changes are needed to attain the outcome. |

| 3. POTENTIAL SUSTAINABILITY: The degree of likelihood to maintain and reproduce the benefits of an intervention in the long run (beyond the implementation period of the intervention). |
| --- |
| In order to calculate the total score for this Q-criterion, proceed as follows: At least 3 ‘A’s, no ‘C’ or ‘D’ = A ; Maximum two ‘C’s, no ‘D’ = B; At least three ‘C’s, no ‘D’ = C ; At least one ‘D’ = D |
| 3.1 Financial/economic viability? |
|  | A | Financial/economic sustainability is potentially very good: costs for services and maintenance are covered or affordable; external factors will not change that. |
|  | B | Financial/economic sustainability is likely to be good, but problems might arise namely from changing external economic factors. |
|  | C | Problems need to be addressed regarding financial sustainability either in terms of institutional or target groups costs or changing economic context. |
|  | D | Financial/economic sustainability is very questionable unless major changes are made. |
| 4.2 What is the level of ownership of the project by target groups and will it continue after the end of external support? |
|  | A | The JLCB and other relevant local structures are strongly involved in all stages of implementation and are committed to continue producing and using results. |
|  | B | Implementation is based in a good part on the JLCB and other relevant local structures, which are also somewhat involved in decision-making. Likeliness of sustainability is good, but there is room for improvement. |
|  | C | Project uses mainly ad-hoc arrangements and the JLCB and other relevant local structures to ensure sustainability. Continued results are not guaranteed. Corrective measures are needed. |
|  | D | Project depends completely on ad-hoc structures with no prospect of sustainability. Fundamental changes are needed to enable sustainability. |
| 4.3 What is the level of policy support provided and the degree of interaction between project and policy level? |
|  | A | Policy and institutions have been highly supportive of project and will continue to be so. |
|  | B | Policy and policy enforcing institutions have been generally supportive, or at least have not hindered the project, and are likely to continue to be so. |
|  | C | Project sustainability is limited due to lack of policy support. Corrective measures are needed. |
|  | D | Policies have been and likely will be in contradiction with the project. Fundamental changes needed to make project sustainable. |
| 4.4 How well is the project contributing to institutional and management capacity? |
|  | A | Project is embedded in institutional structures and contributed to improve the institutional and management capacity (even if this is not a explicit goal). |
|  | B | Project management is well embedded in institutional structures and has somewhat contributed to capacity building. Additional expertise might be required. Improvements in order to guarantee sustainability are possible. |
|  | C | Project relies too much on ad-hoc structures instead of institutions; capacity building has not been sufficient to fully ensure sustainability. Corrective measures are needed. |
|  | D | Project is relying on ad hoc and capacity transfer to existing institutions, which could guarantee sustainability, is unlikely unless fundamental changes are undertaken. |

| Criteria | Score |
| --- | --- |
| Relevance | A |
| Efficiency | C |
| Effectiveness | C |
| Potential sustainability | B |

## Output 1

Output 1: Community Owned Water Supply Organisations are managing rural water supply schemes in a sustainable way.

Initial assessment of the water scheme has revealed that; Most water schemes in the Region and specifically in all targeted water schemes are managed by Water Committees which are under Village Governments and it is further clear that inadequate management of water schemes is among the major factor contributing to inadequate functioning of water schemes.   There is no water Scheme which was found to have a Community Owned Water Supply Organization (COWSO) established as per the Water Supply and Sanitation Act 12 (WSSA) of 2009. In order to reach Output 1, COWSO should be established and strongly strengthened through different approaches. According to the WSSA12 of 2009, COWSO is an independent entity. However, as we report the Government struggling to establish a new management set up of management of rural water supply. The new structure will be under any agency to be known as Rural Water Supply & Sanitation Agency (RUWASA), it will be inaugurated on 1st July 2019. The new set up focusses on sustainability of water schemes. Moreover, the name COWSO will change into Community Based Water Supply Organization. (CBWSO)

As we plan to establish management entities for targeted schemes changes in the structure will be observed. So far process for conducting assessment on COWSO and establishing them is ongoing.

Analysis of progress made

Baseline study hasn’t been conducted

Implementation of planned activities is expected to take place in the 2nd Q of 2019

| Output 1: A1. Community Owned Water Supply Organisations are managing rural water supply schemes in a sustainable way |
| --- |
| Indicators (taken from TFF) | Baseline value | Progress year 1 | Progress year 2 | Progress year 3 | Progress year 4 | End Target | Comments |
| Quality of service to users (based on a number of performance indicators: number of days with intermittent supply, tariffs, etc) | To be defined | N/A yet |  |  |  | To be defined | Baseline not done yet |
| Number of COWSOs with O&M plans | 0 | N/A yet |  |  |  | Minimum 75% of COWSOs have a O&M plans | No COWSO exist in the targeted area |
| COWSOs have a sound accounting system | No COWSO exists | N/A yet |  |  |  | Minimum 85% of COWSOs have a sound accounting system | Baseline not done yet |
| Progress of main activities (taken from TFF) |  | Progress: | Comments (only if the value is C or D) |
|  | A | B | C | D |  |
| A01 Sustainable water supply O&M |  |  |  |  |  |
| A0101 COWSO assessment study |  |  |  |  |  |
| A0102 RAS, LGAs and COWSO capacity development |  |  |  |  |  |
| A0103 C4DEV activities |  |  |  |  |  |
| Analysis of progress made towards output: Analyse the dynamics between the activities and the probable achievement of the Output (see Results Report Guide). |
| Relation between activities and the Output. (how) Are activities contributing (still) to the achievement of the output (do not discuss activities as such?): | N/A yet | N/A yet |
| Progress made towards the achievement of the output (on the basis of indicators): | N/A yet | N/A yet |
| Issues that arose, influencing factors (positive or negative): | N/A yet | N/A yet |
| Unexpected results (positive or negative): | N/A yet | N/A yet |

### Budget execution

The project it is still at the start – up phase, therefore no financial execution related to this activity has been done (no budget expenses yet under this outcome).

### Quality criteria

| Criteria | Score |
| --- | --- |
| Efficiency | N/A yet |
| Effectiveness | N/A yet |
| Sustainability | N/A yet |

## Output 2

Output 2: 200,000 inhabitants have access to safe drinking water that reduces water related burden through rehabilitation and extension of existing assets.

This output would be reached once the water schemes are rehabilitated/re-constructed. Both, design and type of technology have also a strong impact on sustainability. Accordingly, baseline results about causes/reasons of failure of the targeted schemes have to be carefully analysed and avoid them during the design phase.

WASKIRP has already prepared a request for Expression of Interest and TOR for various preliminary works i.e. design study for Mkongoro Gravity Group Scheme, Hydrogeological Study and borehole drilling in 6 water schemes. The documents will be relaunched in early 2019.

Field visits carried out highlight that population of targeted villages has doubled since the period when the schemes were built up to nowadays and drinking water demand has increased considerably. In addition, available surface water has also decreased significantly (due to deforestation, increase of agricultural activities and climate change effects). Finally, some of the targeted schemes need to be rebuilt completely. These facts have strong design and budgetary implications on the rehabilitation or completely constructing new schemes for some of the targeted schemes.

However, through preliminary assessment of the water schemes it has been determined that the actual scheme status is different from what is stated in the TFF. The real situation indicate that the intervention will involve more construction of new schemes from new water sources and the actual budget for the schemes is over 6 Million Euro. This finding has necessitated WASKIRP to reduce the number of beneficiaries’ villages/population from 26/212,214 to 15/122946

### Analysis of progress made

A process to conduct baseline is in preparation. A request for expression of interest has been advertised with a deadline falling to 22nd March 2019.

|  | Output 2: A2. 200,000 inhabitants have access to safe drinking water that reduces water related burden through rehabilitation and extension of existing assets. |
| --- | --- |
| Indicators (taken from TFF) | Baseline value | Progress year 1 | Progress year 2 | Target year 3 | Target year 4 | End Target | Comments |
| Water points functionality | To be defined | N/A yet |  |  |  | Minimum 20% more WPs are functional. | Baseline not done yet. |
| Water quality complying with standards | To be defined | N/A yet |  |  |  | 50 % increase of existing WP which comply with standards. | Baseline not done yet |
| Effective Protection and sustainable management of water catchments (water permits, physical protection, users’ conflicts…) | To be defined | N/A yet |  |  |  | 75% of installed water points are protected and sustainably managed | Baseline not done yet |
| Progress of main activities (taken from TFF) | Progress: | Comments (only if the value is C or D) |
|  | A | B | C | D |  |
| A02 Rural Water Supply schemes rehabilitation and extension |  |  |  |  |  |
| A0201 Design studies and supervision |  |  |  |  |  |
| A0202 Works (catchments, pumping, treatment, reservoirs, distribution lines, DPs) |  |  |  |  |  |
| A0203 Catchment Protection and Management |  |  |  |  |  |
|  | Analysis of progress made towards output |
| Relation between activities and the Output. (how) Are activities contributing (still) to the achievement of the output (do not discuss activities as such?): | N/A yet | N/A yet |
| Progress made towards the achievement of the output (on the basis of indicators): | N/A yet | N/A yet |
| Issues that arose, influencing factors (positive or negative): | N/A yet | N/A yet |
| Unexpected results (positive or negative): | N/A yet | N/A yet |

### Budget execution

The project it is still at the start – up phase, therefore no financial execution related to this activity has been done (no budget expenses yet under this outcome).

### Quality criteria

| Criteria | Score |
| --- | --- |
| Efficiency | N/A yet |
| Effectiveness | N/A yet |
| Sustainability | N/A yet |

## Output 3

Output 3: Households have improved their hygiene practices towards water collection, transport, storage and use.

One of the main causes of water contamination is how the water is handled and stored at household level. Through well targeted hygiene promotion campaigns, better collection and storage practices should contribute to a safer health environment having a positive influence on reaching the expected outcome and impact.

Few communities have indicated that they treat only a little water used for drinking by boiling it or disinfecting it using sodium hypochlorite with a local brand ‘’water guard”). Several others admitted to drink untreated water throughout their lifetime (local brand is “and mothers pay special attention to the treatment of water for kids.

In preliminary designing the Enabel has insisted on including a treatment facility in the schemes to be built or rehabilitated

Awareness targeting hygiene promotion at a household level is of utmost important in this intervention.

### Analysis of progress made

As baseline survey hasn’t been conducted it is difficult to alter initial values stated in the TFF

|  | Output 3: A3 Households have improved their hygiene practices towards water collection, transport, storage and use. |
| --- | --- |
| Indicators | Baseline value | Progress year 1 | Progress year 2 | Target year 3 | Target year 4 | End Target | Comments |
| Progress of main activities | Progress: | Comments (only if the value is C or D) |
|  | A | A | B | C | D |
| A03 Hygiene promotion campaign |  | X |  |  |
| A0301 Knowledge, aptitudes, practices study |  | X |  |  |
| A0302 Hygiene promotion campaign |  | X |  |  |
| A0303 Awareness raising on HIV/AIDS |  | X |  |  |
|  | Analysis of progress made towards output: |
| Relation between activities and the Output. (how) Are activities (still) contributing to the achievement of the output (do not discuss activities as such)?: | N/A yet | N/A yet |
| Progress made towards the achievement of the output (on the basis of indicators): | N/A yet | N/A yet |
| Issues that arose, influencing factors (positive or negative): | N/A yet | N/A yet |
| Unexpected results (positive or negative): | N/A yet | N/A yet |

### Budget execution

The project it is still at the start – up phase, therefore no financial execution related to this activity has been done (no budget expenses yet under this outcome).

| Criteria | Score |
| --- | --- |
| Efficiency | N/A yet |
| Effectiveness | N/A yet |
| Sustainability | N/A yet |

# Transversal Themes

## Gender

Gender has been streamlined in the TFF. Accordingly, during this short reporting period, gender has been included in all developed ToRs for different assignments, in order to identify gender roles, responsibilities and practices related to water access and water management:

- Differential perspectives, roles, needs, and interests of women and men including the practical needs and strategic interests of women and men;

- Relations between women and men pertaining their access to water, representation and decision-making processes;

- Potential disparity impact of project interventions on women and men, girls and boys;

- Social and cultural constraints, opportunities, and entry points for reducing gender inequalities and promoting more equal relations between women and men related to water;

Moreover, Enabel has been keen to consider recruitment of female in among its positions So far Enabel has recruited 1 female among 3 technical staff,3 female against 2 males in its supporting staff. Recruitment of more will continue next year.

## Environment

As for gender issues, environment has also been streamlined in the TFF. The concern is addressed in all assignments developed by WASKIRP. For example; the design studies it is has been emphasized that, Consultants should determine as to which level the environmental assessment will have to be done i.e. should the project involve only Environmental Screening, Initial Environmental assessment or a full environmental impact assessment (EIA).

Flow measurements and water quality analysis have been conducted to ensure that water to be applied/allocated to the schemes complies with the guidelines set by both Water Resources Management Act 11 of 2009 and the Environmental Management Act 20 of 2004

For the purpose of implementing long term water supply schemes and ensuring wild flora and fauna are left with sufficient water within the water catchments more effort has been directed in exploring the possibility of obtaining groundwater for communities in those areas were surface sources have declined considerably  and included in the ToR of the baseline, in order to identify the water needs of the ecosystems as another water users, including vegetation cover (focusing on their role of soil and water resources preservation) and wild fauna and to assess the impact of climate change in the water cycle in targeted areas:

# Steering and Learning

## Action Plan

According to the WASKIRP TFF the focus of the intervention aimed at rehabilitating existing and functional gravitational water schemes, However, the real water status of the schemes revealed that among the selected schemes functional gravity schemes were only highlighted 2 below. The summary below gives the status the entire targeted schemes.

| Sn | Scheme | Type | Remarks |
| --- | --- | --- | --- |
| 1 | Mkongoro Gravity Group Scheme Kigoma district | Functioning Gravity Scheme | Rehabilitation & extension |
| 2 | Kazuramimba Gravity & Pumping Scheme Uvinza district | Non-Functioning Gravity Scheme | Require new scheme from new source |
| 3 | Nyanganga Gravity Scheme Uvinza district | Drying up gravity scheme | Require new scheme from new source |
| 4 | Nyansha Nyantare Gravity Group Scheme Kasulu district | Functioning Gravity Scheme | Rehabilitation extension & augmentation |
| 5 | Mnanila Mwayaya Mkatanga Pumping Scheme Buhigwe district | Non-Functioning gravity scheme | Require new scheme from new source |
| 6 | Kifura Gravity Scheme Kibondo district | Drying up gravity scheme | Require new scheme from new source |
| 7 | Kakonko (Kiziguzigu group) gravity scheme | Dried-gravity scheme | Require new scheme from new source |
| 8 | Kakonko (Urban) | Drying up gravity scheme pumping from boreholes | Rehabilitation, expansion & augmentation |
| 9 | Zeze Boreholes Scheme Kasulu rural | Poor functioning borehole hand pumping scheme | Omitted from the project |

Presented here below is an action plan designed to address the actual water scheme status learned through preliminary assessments.

| Action plan | Source | Actor | Deadline |
| --- | --- | --- | --- |
| Conduct preliminary assessment of the status of the water schemes | Inception report, Mission reports | Project Management team WASKIRP, &PIU | 1st Q to 3rd Q 2018 |
| Identify alternative sources for targeted water schemes | Inception report PIU &JLPC meeting decisions 4th q progress report | Project Management team WASKIRP, &PIU | Q4 2018 |
| Conduct Flow measurement and water quality analysis | Inception report PIU &JLPC meeting decisions Flow measurement & Mission reports, | Project Management team WASKIRP, &PIU | Q3&Q4 2018 |
| Conduct pumping test to existing boreholes in targeted villages | Inception report PIU &JLPC meeting decisions, pumping test & Mission reports | Project Management team WASKIRP, &PIU | Q3 &Q4 2018 |
| Conduct preliminary design and costing of all targeted water schemes | Inception report PIU &JLPC meeting decisions | Project Management team WASKIRP, &PIU | Q3 2018 |
| Review and modify the entire WASKIRP budget | Inception report | Project Management team WASKIRP, RR | Q4 2018 |
| Reduce number of WASKIRP’s | Develop criteria for ranking target water schemes in priority of which | Project Management team WASKIRP, &PIU | Q4 2018 |
|  | Inception report PIU &JLPC meeting decisions | Project Management team WASKIRP, PIU & JLPC | Q4 2018 |
| Hold JLPC | JLPC meeting minutes | Project Management team WASKIRP, PIU & JLPC | Q4 2018 |

- All planned activities were implemented as planned

- WASKIRP area of intervention was reduced to 15 villages with water schemes from the original 26 villages with 9 water schemes

- A list of villages/water schemes selected for further development WASKIRP intervention are tabulated below

| Sn | Selected scheme for WASKIRP Intervention | Recommended Water Supply technology |
| --- | --- | --- |
| 1 | 7 villages of Mkongoro Gravity Group Scheme Kigoma district | Rehabilitate and expand the old gravity scheme |
| 2 | Kazuramimba -Uvinza District | Explore ground water potential, drill boreholes, install pumping units construct storage and distribution infrastructures |
| 3 | Kidyama- Kasulu district |  |
| 4 | 4 Villages of (Kiziguzigu group) Kakonko district | Explore ground water potential drill boreholes, install pumping units construct storage and distribution infrastructures |
| 5 | Kifura - Kibondo district | Explore ground water potential drill boreholes, install pumping units construct storage and distribution infrastructures if not successful abstract surface source from Mkugwa River |
| 6 | Mwayaya -Buhigwe district | Pump from Kivuruga stream. Rehabilitate old tank, Construct storage tank, and distribution system |

## Lessons Learned

| Lessons learned | Target audience |
| --- | --- |
| Surface water has declined so much for the past 30 years in most areas worldwide, among the factors exacerbating the decline include; human induced factors and natural ones. Most of the targeted scheme of which sources have dried up i.e. Mnanila Pumping Group scheme in Buhigwe, Kazuramimba Gravity & Pumping scheme (Uvinza), Kifura pumping & gravity scheme (Kibondo) and 2 gravity sources of Kakonko which were constructed in 1980s are live examples. Exploration of new water sources from both surface and underground would not be avoided in this intervention. | -Project representation Enabel HQ Tanzania & HQ Brussels – -RAS JLPC, -Local beneficiaries and all other stakeholders |
| There are no plans by the Government or from any partner to provide water supply to some of the 11 villages dropped from the formerly targeted 26 WASKIRP villages | Project representation Enabel HQ Tanzania & HQ Brussels |
| Inadequate knowledge of water scheme management in among; established water scheme management entities, LGA leaders, Media and other stakeholders``` contributes highly to inefficient and in-effective performance of the constructed water schemes. Each party responsible on supporting water schemes haven’t prayed their roles as directed. | -Project representation Enabel HQ Tanzania & HQ Brussels – -RAS JLPC, -Local beneficiaries and all other stakeholders |
| Water sources protection and conservation should be given more weight than how it Is considere in the TFF. |  |

Annexes

Original Logical framework

|  | Logical of the intervention | Indicators | Baseline value | Target | Sources of verification | Hypotheses |
| --- | --- | --- | --- | --- | --- | --- |
| GO | Global objective: To contribute toward equitable development and poverty reduction among Kigoma communities through improved access to safe and clean water supply and sanitation services | NSGRP II, BRN WSDPII Key Performance Indicators’ |  |  | WSDP annual sectorial review and report | Government is implementing reforms and programs in particular WSDP II as originally planned |
| SO | Specific objective Increased access to safe drinking water and reduce burden related to water & sanitation amongst communities in Kigoma region, especially women and youths, and use the water as social economic commodity through sustainable interventions on water supply and hygiene practices | % of access to functional water supply (according to national standards) | Access to safe drinking water: % | 90% | MoW water point mapping M&E system MoHSW information system and surveys | Enabling environment for sustainability (financial resources, clear roles & responsibilities, adequate water supply systems) and behaviour change |
|  |  |  | WP functionality: 55% | 90% |  |  |
|  |  | Water borne diseases statistics | To be completed during Comprehensive Baseline Study | Decrease with minimum 20% |  |  |
| R A1 | Result: A1. Community Owned Water Supply Organisations are managing rural water supply schemes in a sustainable way | Quality of service to users (based on a number of performance indicators: number of days with intermittent supply, tariffs, etc…) | N/A as COWSO’s have to be established | Targets of performance indicators to be decided upon during the comprehensive baseline study | Core indicators: LGA’s M&E system Secondary indicators: project M&E system | Capacity to pay for water by final users No conflicts between neighbouring villages sharing water systems |
|  |  | Number of COWSOs with O&M plans | No COWSOs with O&M plans | Minimum 75% of COWSOs have a O&M plans |  |  |
|  |  | COWSOs have a sound accounting system | COWSOs do not have a sound accounting system | Minimum 85% of COWSOs have a sound accounting system |  |  |
| R A2 | Result: A2 200,000 inhabitants have access to safe drinking water that reduces water related burden through rehabilitation and extension of existing assets | Water points functionality | Number of functional WPs in the rural LGAs varies between 22.9% and 69.7% (taking into account the population of the LGAs 51% of the existing WP) The functionality needs to be confirmed during the comprehensive baseline study | Minimum 20% more WPs are functional. | Core indicators: LGA’s M&E system Secondary indicators: project M&E system | Feasibility studies confirms viability of water sources and cost estimates No conflicts between water sources and catchment users |
|  |  | Water quality complying with standards | % of existing water points complying to standards to be determined during the comprehensive baseline study | 50 % increase of existing Water Points which comply with standards. |  |  |
|  |  | Effective protection and sustainable management of water catchments (water permits, physical protection, users’ conflicts…) | % of existing water points with effective protection and sustainable water catchment to be determined during the comprehensive baseline study | 75% of installed Water Points are protected and sustainably managed |  |  |
| R A3 | Result: A3. Households have improved their hygiene practices towards water collection, transport, storage and use | Knowledge, attitude and practises (KAP) related to hygiene (during collection, transport, storage and use – example hand washing) | To be defined during the comprehensive baseline study. | A minimum increase with: 50 % for Knowledge 40 % for Attitude 30% for Practice | Secondary indicators from project M&E system based on focus group discussions and other qualitative methodologies |  |

## Updated Logical framework

Updating of the Logical framework will be made once the Baseline survey is done and base value are determined

## Missions, Meetings

| Meeting/Mission | Date | Fundamental Decision |
| --- | --- | --- |
| 30 Mission Visits | Nov 2017 to Dec 2018 | Result in development of Inception report, Scaling down the scope of WASKIRP intervention |
| Backstopping missions since | July 2018 | Muriel Lambert from Brussels, strategizing decision made by WASKIRP |
| 1st Project Implementation Unit | July 2018 | Facilitate WASKIRP to obtain more information of water schemes and water sources |
| 2nd Project Implementation Unit | Oct 2018 | Scaling down the scope of WASKIRP intervention to correspond wit the available budget |

## “Budget versus current (y – m)” Report

Summary of 2018 Budget

| WASKIRP | TOTAL BUDGET€ | 2018 BUDGET€ |
| --- | --- | --- |
| RESULTS DESCRIPTION | 8.000.000 | 988.080 |
| A - Sustainable water supply and improved hygiene practices | 4.169.597 | 250.000 |
| Result A1 | Sustainable Water Supply O&M | 500.000 | 50.000 |
| Result A2 | Rural Water Supply Schemes Rehabilitation and extension | 3.109.597 | 150.000 |
| Result A3 | Hygiene promotion Campaign | 560.000 | 50.000 |
| B Technical Staff | 1.828.800 | 373.980 |
| X Budgetary Reserve | 308.453 | 0 |
| Z General Means | 1.693.150 | 364.100 |

Summary of the approved budget for 2019

| WASKIRP | TOTAL BUDGET (€) | 2018 |
| --- | --- | --- |
|  |  | BUDGET (€) |
| RESULTS DESCRIPTION | 8.000.000 | 1,868,908 |
| A - Sustainable water supply and improved hygiene practices | 5,085,346 | 1,102,410 |
| Result A1 | Sustainable Water Supply O&M | 448,100 | 155,000 |
| Result A2 | Rural Water Supply Schemes Rehabilitation and extension | 4,257,246 | 847,410 |
| Result A3 | Hygiene promotion Campaign | 380,000 | 100,000 |
| B Technical Staff | 1,576,990 | 384,400 |
| X Budgetary reserve | 80,000 | 0 |
| Z General means | 1.257,664 | 382,098 |

N/A yet because the project is still in its start-up phase.

## Decisions taken by the JLPC and follow-up

Two Joint Local Partners have taken place.   The 1st one was during the project kick-off JLPC meeting, and the second one was on 26 Nov 2018 1 meeting approved only the annual budget for 2018 (Euro. 988,050.00). The second JLPC made several strategic decisions tabulated below

| Decision to take |  |  |  |  | Action |  |  | Follow-up |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Decision to take | Period of identification | Timing | Source | Actor | Action(s) | Resp. | Deadline | Progress | Status |
| Scaling down area of intervention of WASKIRP targeted villages from 26 to 15 | Inception phase | Oct 2018 | Preliminary assessment & Inception report | Project Manager, Project Coordinator Resident Rep, JLPC | Approval of Scaling down area from 26 to 15 by JLPC | Project Management, RR |  | Plan and budget focusses only the selected 15 villages | Project is well focused |
| Modification of WASKIRP works Budget from 54.3 % to 63.6% | Inception phase | October 2018 | Preliminary assessment & Inception report |  | Approval of Modification of WASKIRP works Budget from 54.3 % to 63.6% by JLPC |  |  |  |  |
| Recruitment of the Project Manager | Inception period and beyond | May to Nov 2018 |  |  | Approval of the decision by JLPC |  |  | Project was Manager recruited | The Project Manager proceeds with assigned tasks |
| Introduction of 2 position not in TFF and omitting 2 International consultants | Inception period and beyond | Oct 2018 | Budget Modification & 2018 Progress report |  | Approval of the decision by JLPC |  |  | Processes are on the way to recruit consultants for the 2 positions | In progress |

# Footnotes

Impact is a synonym for global objective, Outcome is a synonym for specific objective, output is a synonym for result

In this document: Impact is a synonym for global objective, Outcome is a synonym for specific objective, output is a synonym for result

Use the formulation of the outcome as mentioned in the logical framework (DTF) or the last version of the logical framework that was validated by the JLCB.

Use the indicators as shown in the logical framework

The value of the indicator at time 0. Refers to the value of the indicators at the beginning of the intervention

The actual value of the indicator at the end of year N-1

The actual value of the indicator at the end of year N. If the value has not changed since the baseline or since the previous year, this value should be repeated.

The target value at the end of year N

The target value at the end of the intervention

Comments about progress realised, namely assessment of the achieved value of the indicator at the end of year N compared to the “baseline” values (time 0) and/or the value of the preceding year, and compared to the expected intermediate value for year N. If the intermediate value is not available, the end target will be the reference. Comments should be limited to a minimum.

The template accommodates up to 3 Outputs (chapters 2.2, 2.3, 2.4). If the intervention has more outputs, simply copy and paste additional output chapters. If the intervention has less than 3 outputs, simply delete the obsolete chapters)

A:	The activities are ahead of schedule

B	The activities are on schedule

C 	The activities are delayed, corrective measures are required.

D 	The activities are seriously delayed (more than 6 months). Substantial corrective measures are required.

If the Logical Framework contains more than three Outputs, copy-paste the 2.4 chapter and create 2.6 for Output 4 , 2.7 for Output 5, etc.

See also Section  3.5, Table 13. “Preliminary targets for water access indicators”

See “Water Point Mapping System (WPMS) Tanzania Official Website”, data of 2014 (http://wpm.maji.go.tz/)