## ID (hidden)
Result | Indicator/Progress Marker Updated at ToC workshop | Baseline Muni | Baseline Kaliro | Baseline Mubende | Baseline Kabale | Data end of 2017 | [5 empty] | Data for end of 2018 | [5 empty] | Data for end of 2019 | [5 empty] | Target (2020) | Source/ Means of Verification | Frequency | Resp. person | Budget | Comments | Remarks
[6 empty] | Kabale | Kaliro | Mubende | Muni | Unyama | Average | Kabale | Kaliro | Mubende | Muni | Unyama | Average | Kabale | Kaliro | Mubende | Muni | Unyama | Average
Output Area 1.2: Strategic management and implementation capacity of NTCs strengthened
Capacity development | Average performance score given by NTC staff (organisational self-assessment) | Tools and strategy revised in July 2017 to enrich former self-assessments conducts by SDHR | [14 empty] | To be conducted during final year of project | [6 empty] | Target for priority areas : 3.5 Target for non-priority areas : 3.0 | Project reports and data | Annually | ID team | No cost
Capacity development | % of implementation of NTCs training plans | 0% | 0% | 0% | 0% | [5 empty] | 28% | 46.7% | 25.7% | 50% | 48.3% | 48.4% | 76% | [6 empty] | 100% | NTC Progress reports (SDHR) | Annually | ID team | No cost
Capacity development | % of implementation of NTCs capacity development plans | Plans developed in September 2017 | [8 empty] | FY ongoing | 0% | 29% | 0% | 85% | 30% | 28.8% | [6 empty] | 80% | NTC Progress reports , (Grant agreement) | Annually | ID team | No cost
Staff management | Time on Task (academic and admin staff) (M/F) | No formal monitoring mechanism | TBD | TBD | TBD | [5 empty] | No formal monitoring mechanism | [5 empty] | 62 hrs | [6 empty] | TBD | NTC records | Annually | NTCs | No cost
Academic and financial management | Number of NTCs whose academic management processes are digitalized | 0 (Smart Campus not operational) | 0 | 0 | [6 empty] | 0 (Smart Campus not operational) | [5 empty] | 0 (Smart Campus not operational) | [6 empty] | 4 | NTC records | Annually | ID team | No cost
Academic and financial management | Number of NTCs whose financial management processes are digitalized | 0 (Smart Campus not operational) | 0 | 0 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 5 | [6 empty] | 5 | NTC records | Annually | ID team | No cost | All colleges are now using the e-vote book system for financial management
IT management | Availability of Internet connectivity | Unknown | Unknown | Unknown | Unknown | [5 empty] | monitoring mechanism not harmonised | [5 empty] | 69.5% | [6 empty] | 90% | NTC records | Annually | NTCs | No cost
Financial management | Execution rates (global / Grants agreements) | - | - | - | - | [5 empty] | FY ongoing | 65% | 66% | 69% | 60% | 67% | 65.4% | [6 empty] | 90% | NTC financial reports | Annually | Financial team | No cost
Financial management | % of rejected expenditures | - | - | - | - | [5 empty] | Fisrt finacial report not yet approved | 1% | 1% | 11% | 1% | 0% | 2.8% | [6 empty] | Less than 5% | NTC financial reports | Annually | Financial team | No cost
Safe Learning Environment | Number of NTCs integrating violence/SLE in their annual action and budget plan | Plans developed for Fiscal Year 2017/18 | 0 | 0 | 0 | [5 empty] | 5 | 1 | 1 | 1 | 1 | 1 | 5 | [6 empty] | 5 | NTC annual plan | Annual | M&E team | No cost | An indicator on SLE is in the 5 NTCs' workplans: Activities promoting safe learning organised
Output Area 1.3: TIET strengthened
Capacity development | SDHR: Overall performance score given by TIET members during organizational self-assessment exercise | 2,6 (on a scale from 1-4) | [8 empty] | SDHR self assessment not updated | [5 empty] | To be conducted during final year of project | [6 empty] | 3.0 | Project data | Annually | ID team | No cost
Capacity development | % of implementation of TIET training plan | 0% | 0% | 0% | 0% | [5 empty] | 8% | [5 empty] | 54% | [6 empty] | 100% | TIET Progress reports | Annually | ID team | No cost | Out of 13 planned trainings, 7 were implemented
Operational management | Number of quarterly reviews for TIET | No formal monitoring mechanism | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 4 | [6 empty] | 4 | TIET Progress reports | Annually | ID team | No cost
TIET’s vision for policy design | Availability of a long term strategic plan for Teacher Training in Uganda | 0 | [8 empty] | 0 | [12 empty] | 1 | Policy document | End of the project | ID team | No cost
TIET as pilot of the whole teacher training system | Integrated monitoring system in place for PTE and ITE | 0 | [8 empty] | 0 | [12 empty] | 2 | TIET Progress reports | End of the project | ID team | No cost
Output Area 1.4: CMU and PDU strengthened
Guidelines for sustainable infrastructures | Number of guidelines disseminated | 0 | [8 empty] | 0 | [5 empty] | 0 | [6 empty] | 1per priority areas | CMU report | Annually | ID and Infra team | No cost
Capacity development | SDHR: Overall performance score given by CMU members during organizational self-assessment exercise | ???? (on a scale from 1-4) | [8 empty] | SDHR self assessmnet not updated | [5 empty] | To be conducted during final year of project | [6 empty] | 3.0 | CMU report | Mid-term + Final evaluation report | ID and Infra team | No cost
Capacity development | % of implementation of CMU training plan | 0% | 0% | 0% | 0% | [5 empty] | 15% | [5 empty] | 56% | [6 empty] | 100% | CMU report | Annually | ID and Infra team | No cost | Out of 9 planned trainings, 5 were implemented
Efficiency of the service delivery | Level of timeliness of the procurements done by PDU | Criteria to be defined during baseline study | [8 empty] | baseline study not accepted by beneficiary | [12 empty] | Criteria to be defined after baseline study | Baseline + End of project studies | End of the project | ID team | 10 000 €
Capacity development | SDHR: Overall performance score given by PDU members during organizational self-assessment exercise | 1,4 (on a scale from 1-4) | [8 empty] | SDHR self assessmnet not updated | [5 empty] | To be conducted during final year of project | [6 empty] | 3.0 | PDU report | Mid-term + Final evaluation report | ID and Infra team | No cost
Capacity development | % of implementation of PDU training plan | 0% | 0% | 0% | 0% | [5 empty] | 0% | [5 empty] | 70% | [6 empty] | 100% | PDU report | Annually | ID and Infra team | No cost | 7 out of 10 planned trainings were implemented
Note on B4: BTCCTB: SDHR
Note on B5: BTCCTB: SDHR
Note on B6: BTCCTB: data from grant agreement(2017/2018) Activities related to capacity development plan (B.7.1)
Note on B7: Personal: Indicator is not clear
Note on B9: BTCCTB: Insert new row for acdemic mgt processes
Note on B11: BTCCTB: Grant agreement to be considered
Note on B12: BTCCTB: get from philip- grant agreemt
Note on B13: Windows User: Hannah
Note on B15: BTCCTB: review kaliro TFF
Note on C15: Personal: Don't understand 2,6
Note on B16: BTCCTB: from SDHR
Note on B17: BTCCTB: inquire from Abdul
Note on B23: BTCCTB: SDHR
Note on B26: BTCCTB: SDHR

## INFRA (hidden)
Result | Indicator/Progress Marker Updated at ToC workshop | Baseline Muni | Baseline Kaliro | Baseline Mubende | Baseline Kabale | Data end of 2017 | [5 empty] | Data for end of 2017 | Data for end of 2018 | Data for end of 2019 | [5 empty] | Target (2020) | Source/ Means of Verification | Frequency | Resp. person | Budget | Comments | Remarks | Remarks
[6 empty] | Kabale | Kaliro | Mubende | Muni | Unyama | Average | Average |  | Kabale | Kaliro | Mubende | Muni | Unyama | Average
Effective use of facilities | % of implementation of new and renovated NTC facilities (infrastructure component) | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 9% | [6 empty] | 100% | Infrastructure reports | Annually | NTCs | No cost | now 66% average physical progress |  | We can only provide the infrastructure but are not responsible for an effective use of it..
Access to quality training and learning facilities | Number of infrastructure constructed according to benchmarked standards of the sustainable and renewable energy designs | 0 dormitories 0 training facilities | 0 dormitories 0 training facilities | 0 dormitories 0 training facilities | 0 dormitories 0 training facilities | [5 empty] | 0 | 0 | 0 | 78% | 62.5% | 34% | 84.5% | 0 | 64.75% | 4 | Progress reports on implementation of master plan | Annually | Infra Team | No cost | This is physical infrastructure progress | Think later on on analysing occupation rate
Maintenance of training and learning facilities | Number of NTCs with operational maintenance and assets management plan in place | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 45% | 45% | 45% | 45% | 45% | 45% | 5 | Data from maintenance system, NTC facilities | Annually | ID and Infra team | No cost | Based on TFF Muni |  | Masterplan done / budgets annually done / operational decision model data being gathered / awareness trainings ongoing / training staff ongoing /
Note on B5: BTCCTB: discuss with Nobert

## PEDAGOGY (hidden)
Result | Indicator/Progress Marker Updated at ToC workshop | Baseline Muni | Baseline Kaliro | Baseline Mubende | Baseline Kabale | Data end of 2017 | [5 empty] | Data for end of 2018 | [5 empty] | Data for end of 2019 | [5 empty] | Target (2020) | Source/ Means of Verification | Frequency | Resp. person | Budget | Comments | Remarks
[6 empty] | Kabale | Kaliro | Mubende | Muni | Unyama | Average | Kabale | Kaliro | Mubende | Muni | Unyama | Average | Kabale | Kaliro | Mubende | Muni | Unyama | Average
Output Area 3: Pedagogical approaches to pre- and in-service teacher training effectively applied at NTC and in partner schools.
Strengthened pedagogical support | Average satisfaction of female and male academic staff with the amount and quality of pedagogical support provided by KYU (on a scale from 1 to 4) |  |  |  |  | 2.8 (3 F,2.6 M) | 2.25 (2.3 F,2.2M) | 2.7 (2.6 F,2.8M) | 2.55 (2.8 F,2.3 M) | 2.5 (2.8 F,2.2 M) | 2.5 | [5 empty] | To be conducted in 2019 | (2.2 F, 2.8 M) | (1.0 F, 2.3 M) | (1.5 F, 3.3 M) | (2.9 F, 2.2 M) | (2.0 F, 2.5 M) | 2.5 | 3 | Project survey data | Mid-term + end of project | Peda team | 8,000 EUR
Strengthened pedagogical support | Average satisfaction of female and male pedagogic staff with the amount and quality of support provided by mentors in the NTCs (mentorship system) (on a scale from 1 to 4) |  |  |  |  | 2.85 (F 2.9, M 2.8) | 2.25 (2.1 F,2.4M) | 2.9 (2.8 F,3 M) | 3.05 (2.9,3.2) | 2.7 (2.8,2.6) | 2.7 | [5 empty] | To be conducted in 2019 | (3.1 F, 3.0 M) | (2.8 F, 2.8 M) | (4.0 F, 3.3 M) | (3.3 F, 2.4 M) | (2.6 F, 2.4 M) | 2.7 | 3 | Project survey data | Mid-term + end of project | Peda team | 8,000 EUR
Strengthened professional competencies of NTC academic staff | Average satifaction expressed by pedagogic staff (F/M) following Continuous Professional Development activities (professional development modules, support supervision system, training…) (on a scale from 1 to 4) |  |  |  |  | 2.85 (2.8 F, 2.9 M) | 2.4 (2.2 F, 2.6 M) | 2.95 (2.9 F, 3M) | 3.15 (3.1 F, 3.2 M) | 2.75 (2.8 F,2.7M) | 2.8 | [5 empty] | To be conducted in 2019 | (3.0 F, 2.9 M) | (2.5 F, 2.5 M) | (3.0 F, 3.3 M) | (3.2 F, 2.5 M) | (2.7 F, 2.5M) | 2.7 | 3 | Project survey data CPD reports | Mid-term + end of project | Peda team NTC | No cost
Increased access to information and pedagogical content | Average satisfaction of female and male pedagogical staff regarding the libraries and ICT facilities (on a scale from 1 to 4) |  |  |  |  | 2.3 (2.5 F, 2.1M) | 2.65 (2.6 F, 2.7M) | 2.25 (2.3 F, 2.2 M) | 2.7 (2.5 F, 2.9 M) | 2.8 (2.8 F,2.8 M) | 2.5 | [5 empty] | To be conducted in 2019 | 2.4F, 2.5M | 2.6F, 2.6M | 2.1F, 2.2M | 2.8F, 2.6M | 2.7F, 2.8M | 2.6 | 3 | Project survey data | Mid-term + end of project | Peda team | No cost
Increased access to information and pedagogical content | Average satisfaction of female and male students regarding the libraries and ICT facilities (on a scale from 1 to 4) | To be collected | To be collected | To be collected | To be collected | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | 2.8 | 2.8 | 2.1 | 2.5 | 2.9 | 2.6 | 2.8F, 2.8M | 3F, 2.9M | 2.5F, 2.6M | 2.8F, 2.7M | 3F, 2.9M | 2.8 | 3 | Project survey data | Mid-term + end of project | Peda team NTC librarians | No cost
Increased access to information and pedagogical content | Level of application by lecturers of ICT in teaching and learning (on a scale from 1 to 4) |  |  |  |  | 2.27 (2.05 F, 2.5 M) | 2.85 (2.8 F, 2.9 M) | 2.9 (2.7 F, 3.1M) | 2.97 (2.6 F, 3.35 M) | 2.5 (2.5 F,2.5 M) | 2.7 | 3 | 2.1 | 2.5 | 3.3 | 2.1 | 2.6 | 2.8F, 2.5M | 3.3F, 2.9M | 3.3F, 3.4M | 2.8F, 2.7M | 3.1F, 2.3M | 2.7 | 2.5 | Classroom observation tool Project survey | Annually | NTC mentors | No cost
School practice turned into a learning tool | Level of application by NTC students of ATL in continuous school practice (on a scale from 1 to 4) | 0,0 | 0,0 | 0,0 | 0,0 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | 3.2, 3.3 | 3.1, 3.1 | 3.3, 3.2 | 3.3, 3.4 | 3, 3.1 | 3.2 | [6 empty] | 2.5 | Classroom observation tool Site Visit continuous school practice reports | Annually | School practice officer | No cost
School practice turned into a learning tool | % of DES students (M/F) doing CSP activities in the NTC and in the partner secondary schools | 0,0 | 0,0 | 0,0 | 0,0 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | [5 empty] | 98.73% | 50% | 59% | 99% | 71% | 94% | 74.6% | 75% | Continuous school practice reports | Annually | School practice officer | No cost
Partner secondary schools strengthened | Level of application by secondary school teachers of ATL (on a scale from 1 to 4) | To be collected | To be collected | To be collected | To be collected | 2.8 | 3 | 2.8 | 2.7 |  | 2.7 | [5 empty] | To be conducted in 2019 | 3.0 (3F, 3M) | 2.6 (2.7F, 2.6M) | 2.9 (3F, 2.9M) | 3.1 (3.2F, 3M) | 3.0 (3F, 3M) | 2.9 (2.9F, 2.9M) | 2.5 | Classroom observation tool Site Visit Pre and post test | Annually | NTC mentors | No cost
Partner secondary schools strengthened | % of partner secondary schools trained in violence prevention and response | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | [6 empty] | 80% | Training reports | Annually | Peda team | No cost
Pedagogical activities supported | Number of DES students submitting personal projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | increasing number from year to year | NTC reports | Annually | Peda team | No cost
Pedagogical activities supported | Number of lecturers developing /publicating researches (action or academic) | 1 | 0 | 15 | 0 | 0 | 1 | 19 | 3 | 0 | 23 | 2 (2M) | 28 (6, 22) | 12 (3F, 9M) | 29 (7F, 22M) | 8 (4F, 4F) | 79 (20F, 59M) | 2 (2M) | 12 (5F, 7M) | 10 (2F, 8M) | 19 (7F, 12M) | 7 (5F, 2M) | 50 (19F, 31M) | increasing number from year to year | NTC CPD reports | Annually | Peda team NTC | No cost
Effective use of pedagogical competences within NTCs | Level of application by lecturers of ATL within NTCs (M/F) (on a scale from 1 to 4) | [9 empty] | 3 | 3.4 | 3.1 | 3.2 | 3.4 | 3.1 | 3.2 | (3.0 F, 2.8 M) | (2.7 F, 2.7 M) | (3.1 F, 3.1 M) | (3.0 F, 2.6 M) | (2.7 F, 3.0 M) | 2.8 | 3.5 |  | Annually | Peda team NTC
50
Note on B4: BTCCTB: planned for 2019
Note on B5: BTCCTB: for 2019
Note on B6: BTCCTB: for 2019
Note on B7: BTCCTB: for 2019
Note on L9: Nie: Survey declaration: I use ICT for preparing my lessons, I use ICT into my lessons as a resource tool for all students
Note on B12: Personal: Data to be collected by mentors
Note on G12: Personal: Data at the end of 2017 here is based on post-test scores for ATL training.
Note on C15: Nie: Baseline: NTC RBM review October 2017
Note on D15: Nie: Baseline: NTC RBM review October 2017
Note on E15: Nie: Baseline: NTC RBM review October 2017
Note on F15: Nie: Baseline: NTC RBM review October 2017

## SDHR (hidden)
Result | Indicator/Progress Marker Updated at ToC workshop | Data end of 2017 | Data for end of 2018 | Data for end of 2019 | [5 empty] | Target (2020) | Source/ Means of Verification | Frequency | Resp. person | Budget | Comments | Remarks
|  | Average | Average | Kabale | Kaliro | Mubende | Muni | Unyama | Average
Capacity development | Average performance score given by NTC staff (organisational self-assessment) |  | To be conducted during final year of SDHR project | 2.85 | 2.24 | 2.51 | 2.65 | 2.97 | 2.56 | Target for priority areas : 3.5 Target for non-priority areas : 3.0 | Project reports and data | Annually | ID team | No cost
Capacity development | % of implementation of NTCs training plans | 28% | 76% | 100% | 65% | 85% | 85% | 80% | 83% | 100% | NTC Progress reports (SDHR) | Annually | ID team | No cost
Capacity development | SDHR: Overall performance score given by TIET members during organizational self-assessment exercise | SDHR self assessment not updated | To be conducted during final year of SDHR project | [5 empty] | 3.03 | 3.0 | Project data | Annually | ID team | No cost
Capacity development | % of implementation of TIET training plan | 8% | 54% | [5 empty] | 85% | 100% | TIET Progress reports | Annually | ID team | No cost
Capacity development | SDHR: Overall performance score given by CMU members during organizational self-assessment exercise | SDHR self assessmnet not updated | To be conducted during final year of SDHR project | [5 empty] | 2.1 | 3.0 | CMU report | Mid-term + Final evaluation report | ID and Infra team | No cost |  | To be collected at SDHR
Capacity development | % of implementation of CMU training plan | 15% | 56% | [5 empty] | 0% | 100% | CMU report | Annually | ID and Infra team | No cost |  | There were no trainings conducted in 2019
Capacity development | SDHR: Overall performance score given by PDU members during organizational self-assessment exercise | SDHR self assessmnet not updated | To be conducted during final year of SDHR project | [5 empty] | 2.98 | 3.0 | PDU report | Mid-term + Final evaluation report | ID and Infra team | No cost |  | To be collected at SDHR
Capacity development | % of implementation of PDU training plan | 0% | 70% | [5 empty] | 0% | 100% | PDU report | Annually | ID and Infra team | No cost |  | There were no trainings conducted in 2019
Note on B3: BTCCTB: Overall score Kabale : 2.44 Overall score Mubende : 2.11 Reference:- Mubende-Kabale TFF, pg.109, For Baseline 2016
Note on B4: BTCCTB: SDHR
Note on B6: BTCCTB: from SDHR
Note on B8: BTCCTB: SDHR
Note on B10: BTCCTB: SDHR

## M&E Matrix
Last update of data: 19 April 2021
INTEGRATED MONITORING MATRIX TTE PROJECT
Result | Indicator/Progress Marker | Baseline Muni | Baseline Kaliro | Baseline Mubende | Baseline Kabale | Data end of 2017 | [5 empty] | Data for end of 2018 | [6 empty] | Data for end of 2019 | [6 empty] | Data for end of 2020 | [5 empty] | Target (2020) | Source/ Means of Verification | Frequency | Resp. person | Budget | Comments on 2020 data
[6 empty] | Kabale | Kaliro | Mubende | Muni | Unyama | Average | Kabale | Kaliro | Mubende | Muni | Unyama | Average/Total | Comments on 2019 data | Kabale | Kaliro | Mubende | Muni | Unyama | Average/Total | Comments on 2019 data | Kabale | Kaliro | Mubende | Muni | Unyama | Average/Total
Global objective / Impact: Increased access to quality post- primary education and training, as part of Universal Post-Primary Education and Training (UPPET)
Use of skills / competences in post - primary education and training | Extent to which NTC graduates (male and female) have become teachers in secondary schools and/or training institutes and who indicate that they have been able to apply their teaching skills | - | - | - | - | [11 empty] | Tracer Study not yet done | Certificates not available since 2014 | 83% | 84% | 72% | 83% | 82% | 81% (M=86%, F=68%) | Data was from the Tracer Study report done in 2019 for 2017 NTC graduates. | [5 empty] | 0% | - | Tracer study / questionnaires to be sent out to NTC graduates | Beginning and end of project | NTCs KYU |  | Tracer Study was not conducted in 2020. 2019 exams have not been moderated yet.
Quality of post-primary education | S4 completion rate | Completion rate: 37,8% Passing rate: 95,7% | Completion rate: 37,8% Passing rate: 95,7% | Completion rate: 37,8% Passing rate: 95,7% | Completion rate: 37,8% Passing rate: 95,7% | [5 empty] | Completion rate: 37,8% Passing rate: 87% | [5 empty] | Completion rate: 34.8% Passing rate: 91% | Completion rate in exams 2017: Source of data was the annual statistical abstract (UBOS 218). Passing rate for S.4 students that sat in 2017: Source of data was annual performance report for FY 2017/2018 | [5 empty] | Completion rate: - Passing rate: 87.2% | Passing rate for S.4 students that sat in 2018: Source of data was annual performance report (ESSAPR) for FY 2018/2019 | [5 empty] | Passing rate: 92% (91%F, 93%M) | Completion rate: 100% Passing rate: 100% | Joint Assessment Framework MoES annual performance reports TIET annual performance reports | Annually | MOES | No cost | Passing rate for S.4 students that sat in 2019: Source of data was annual performance report (ESSAPR) for FY 2019/2020
Quality of post-primary education | % of students reaching defined levels of average competence in selected subjects / learning areas in (non-) target schools. | English S2 : 49,3% Maths S2 14/15: 41,5% Sciences (Biology) S2: 20,5% | English S2 : 49,3% Maths S2 14/15: 41,5% Sciences (Biology) S2: 20,5% | English S2 : 49,3% Maths S2 14/15: 41,5% Sciences (Biology) S2: 20,5% | English S2 : 49,3% Maths S2 14/15: 41,5% Sciences (Biology) S2: 20,5% | [13 empty] | - | - | - | - | - | - |  | - | - | - | - | - | - | English S2: 100% Maths S2: 100% Sciences (Biology) S2: 100% | Joint Assessment Framework MoES annual performance reports TIET annual performance reports | Annual | MOES | No cost | there is no updated data
Specific objective / Outcomes: NTCs produce competent teachers through: 1) effective use of acquired management, 2) proper use of improved infrastructure and facilities, and 3) pedagogical competencies
Competent teachers | Number of NTC graduates matching the teacher competency profile (passing rates) (M/F). |  |  | Passing rate : - Total : 91,2% - Men : 89.7% - Women : 94.1% | Passing rate : - Total : 91,4% - Men : 95,1% - Women : 84,1% | 95% (F=84%,M=106%) | 80% (F=86%,M=74%) | 70% (F=83%,M=58%) | 95% (F=99%,M=92%) | 83% (F=85%,M=82%) | 86% (F=86%, M=85%) | 100% (M=62%, F=38%) | 79% | 96% (M=99%, F=91%) | 102% (M=100%, F=107%) | 83% (M=80%, F=91%) | 92% | The data was provided by the NTCs and its for students who enrolled in 2015/2016 academic year |  | 98% (M=99%, F=96%) |  |  | 89% (M=89%, F=91%) | 94% | The data was provided by the NTCs and its for students who enrolled in 2017/2018 academic year. | [5 empty] | 0% | Passing rates on graduation remain at least at the same level with no significant differences between the scores of boys and girls. | NTC reports | Annual (academic year) | BTC FC |  | The data for students who enrolled in 2019/2020 academic year not yet available.
Effective management | Existence of Annual Work-plans for each Institutions | No integrated mechanism for planning, budgeting and monitoring | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 5 |  | 1 | 1 | 1 | 1 | 1 | 5 | Workplans for FY 2019/2020 are available and in use in the 5 NTCs | 1 | 1 | 1 | 1 | 1 | 5 | 5(1/NTC) | Institutions’ work-plan | Annual | ID team | No cost | Workplans for FY 2019/2020 are available and in use in the 5 NTCs
Effective management | % of progress of implementation of each annual Action Plans | No integrated mechanism for planning, budgeting and monitoring | No data available as action plan are yet to be refined | No data available as action plan are yet to be refined | No data available as action plan are yet to be refined | [5 empty] | FY ongoing | 63% | 54% | 64% | 82% | 38% | 60% | Average is of activities in the NTC workplans of FY 2017/2018 whose execution rate at least 80% | 67% | 30% | 51% | 84% | 50% | 56% | Average is of activities in the NTC workplans of FY 2018/2019 whose execution rate was at least 80% | - | - | - | - | - | - | At least 70% of the planned activities are successfully implemented. | Annual report /institutions | Annual | PC/PCC | No cost | Data not available as it is meant to be got from the NTCs' RBM reports; FY 2019-2020. Hidering factors include the COVID-19 pandemic and closure of NTCs
Effective use of facilities | % of implementation of new and renovated NTC facilities (infrastructure component) | 0 | 0 | 0 | 0 | [5 empty] | 0 | 22% | 8% | 5% | 8% | 0% | 8.6% | Source of data are the physical construction inspection reports; December 2018 | 90% | 77.5% | 38% | 91.5% | - | 74% | This is based on the physical progress; December 2019 | 100% | 100% | 68% | 100% | 100% | 93.6% | 100% | Infrastructure reports | Annually | NTCs | No cost | This is based on the physical progress; December 2020
Effective use of pedagogical competences within NTCs | Level of application by lecturers of ATL within NTCs (M/F) (on a scale from 1 to 4) | TTE data for 2016: Average score for the use of ATL methods by teaching staff, as assessed during classroom observations in supported colleges. |  |  | 3,2 | 3.1,3 | 2.9,2.7 | 2.8,3 | 3,3.2 | 3,2.9 | 3 | 3.4 | 3.1 | 3.2 | 3.4 | 3.1 | 3.2 | The source of the data was the class observation exercise of NTC lecturers' lessons in the 5 NTCs (Nov 18, by mentors and NE). | 2.9 (3.0 F, 2.8 M) | 2.7 (2.7 F, 2.7 M) | 3.1 (3.1 F, 3.1 M) | 2.8 (3.0 F, 2.6 M) | 2.9 (2.7 F, 3.0 M) | 2.9 (2.9 F, 2.8 M) | The source of the data was the pedagogy survey results; self delaration by NTC lecturers in the 5 NTCs (August 19, Questionnaires were used for data collection). | 3 | 2.5 | 2.9 | 2.9 | 2.9 | 2.8 | 3.5 | Classroom observation tool Project survey | Annually | Peda team Mentor teachers | No cost | The source of the data was the survey results (December 2020, Questionnaires were used for data collection).
Output Area 1.1: Supervision and Monitoring System in place for the Secondary teacher education system (5 NTCs + TIET)
Strengthened M&E framework | Number of quarterly meetings at each level | No formal monitoring mechanism | To be collected | To be collected | To be collected | [5 empty] | 2 | 4 | 4 | 4 | 4 | 4 | 4 | RBM workplans of the NTCs which were received at the end of each quarter were the source of the information (The management meeting at NTC level was the MOV) | 4 | 4 | 4 | 4 | 4 | 4 | RBM workplans of the NTCs for FY 2018/2019 which were received at the end of each quarter were the source of the information (The management meeting at NTC level was the MOV) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | NTC and TIET reports | Quarterly | ID team | No cost | 2 meetings were at college level and the other 2 were done online; source of the data are the reports received from the NTCs (Excel and word documents were received)
Strengthened M&E framework | Data completion rates | No formal monitoring mechanism | - | - | - | [5 empty] | Q1: 79% Q2: 93% | Q1: 63% Q2: 89% Q3: 77% Q4: 85% | Q1: 87% Q2: 89% Q3: 86% Q4: 94% | Q1: 51% Q2: 79% Q3: 84% Q4: 87% | Q1: 90% Q2: 90% Q3: 90% Q4: 91% | Q1: 78% Q2: 81% Q3: 80% Q4: 93% | Q1: 74% Q2: 85% Q3: 84% Q4: 90% Average: 83.3% | With FY 2017-18 considered, data completion rates for FY Q1-Q4 per NTC were calculated to get these results | Q1: 73% Q2: 77% Q3: 87% Q4: 95% | Q1: 66% Q2: 69% Q3: 95% Q4: 94% | Q1: 58% Q2: 78% Q3: 69% Q4: 79% | Q1: 91% Q2: 97% Q3: 93% Q4: 97% | Q1: 70% Q2: 77% Q3: 78% Q4: 72% | Q1: 72% Q2: 80% Q3: 84% Q4: 87% Average: 81% | With FY 2018-19 considered, data completion rates for FY Q1-Q4 per NTC were calculated to get these results | - | - | - | - | - | - | 80% | NTC and TIET reports | Quarterly | ID team | No cost | With FY 2019-20 considered, data could not be compiled as it is meant to be got from the NTCs' RBM reports. Hidering factors include the COVID-19 pandemic and closure of NTCs
Output Area 1.2: Strategic management and implementation capacity of NTCs strengthened
Capacity development | Average performance score given by NTC staff (organisational self-assessment) | 2.68 | 1.89 | 1.99 | 2.69 | [11 empty] | To be conducted during final year of SDHR project |  | 2.85 | 2.24 | 2.51 | 2.65 | 2.97 | 2.56 | Data was provided by SDHR | n/a | [5 empty] | Target for priority areas : 3.5 Target for non-priority areas : 3.0 | Project reports and data | Annually | ID team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Capacity development | % of implementation of NTCs training plans | 0% | 0% | 0% | 0% | [5 empty] | 28% | 100% | 47% | 77% | 79% | 80% | 76% | Data was provided by SDHR | 100% | 65% | 85% | 85% | 80% | 83% | Data was provided by SDHR | n/a | [5 empty] | 100% | NTC Progress reports (SDHR) | Annually | ID team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Capacity development | % of implementation of NTCs capacity development plans | Plans developed in September 2017 | [8 empty] | FY ongoing | 0% | 29% | 0% | 85% | 30% | 28.8% | Data source was the Grants financial reports FY 2017-2018 | 101% | 0% | 90% | 107% | 106% | 80.8% |  | 0% | 99% | 100% | 41% | 84% | 64.8% | 80% | NTC Progress reports , (Grant agreement) | Annually | ID team | No cost | Implementation affected by lock down due to COVID-19
Staff management | Time on Task (academic and admin staff) (M/F) - Number of days at station per month (%) | No formal monitoring mechanism | TBD | TBD | TBD | [5 empty] | No formal monitoring mechanism | 65 hrs | 33 hrs | 61 hrs | 104 hrs | 47 hrs | 34% | Data presented is from the daily attendance tool for the academic staff for the month of October, 2018 | 49% | 27% | 26% | 34% | 44% | 36% | On average, in a period of 6 months (June to Dec, 2019) staff were at the college atleast 36% of each month which can be translated into approximately 2.5 days or 20hrs in aweek | 18% | 14% | 10% | 12% | 11% | 13% | Increasing number of hours per year (160 hrs or 100% being the maximum) | NTC records | Quarterly | NTCs | No cost | On average, in a period of 6 months (Jan-March & Oct-Dec, 2020) staff were at the college atleast 13% of each month which can be translated into approximately 2.5 days or 20hrs in aweek
Academic and financial management | Number of NTCs whose academic management processes are digitalized | 0 (Smart Campus not operational) | 0 | 0 | [6 empty] | 0 (Smart Campus not operational) | [5 empty] | 0 (Smart Campus not operational) | Based on the evaluation of smart campus, an assessment of an alternative acdemic softwares is ongoing | 0 | 0 | 0 | 0 | 0 | 0 | The evaluation and procurement of a new academic system is in the final stages | 0 | 0 | 0 | 0 | 0 | 0 | 4 | NTC records | Annually | ID team | No cost | The academic management system was partially installed in Unyama and Kaliro. It was presented in Muni but not yet installed. Plans for installation are underway in the 1st quarter of 2021
|  | 0 (financial management digitalized) | [8 empty] | 0 (financial management digitalized) | 1 | 1 | 1 | 1 | 1 | 5 | All colleges are piloting progressive digitalization (e-vote book) | 1 | - | - | 1 | 1 | 3 | Installation for Quick books (contemporary financial software to replace e-votebook) commenced in 2019 in 3 NTCs. The exercise will take placein the remaining 2 NTCs in 2020. | 1 | - | - | 1 | 1 | 3 | 5 | NTC records | Annually | ID team | No cost | The installation in the remainig 2 NTCs is not yet done.
IT management | Availability of Internet connectivity | Unknown | Unknown | Unknown | Unknown | [5 empty] | monitoring mechanism not harmonised | Q1: 69% Q2: 80% | Q1: 98% Q2: 60% | Q1: 40% Q2: 60% | Q1: 90% Q2: 91% | Q1: 43% Q2: 64% | Q1: 68% Q2: 71% | Results considered are those of FY 2018-2019. Thats when the NTCs actively started utilizing the harmonised designed monitoring system | Q1: 69% Q2: 80% Q3: 40% Q4: 60% | Q1: 98% Q2: 60% Q3: 65% Q4: 50% | Q1: 40% Q2: 60% Q3: 2% Q4: 62% | Q1: 90% Q2: 91% Q3: 94% Q4: 100% | Q1: 43% Q2: 64% Q3: 69% Q4: 75% | Q1: 68% Q2: 71% Q3: 54% Q4: 69% =66% | Results considered are those of FY 2018-2019 NTC RBM reports. | [6 empty] | 90% | NTC records | Annually | NTCs | No cost | With FY 2019-20 considered, data could not be compiled as it is meant to be got from the NTCs' RBM reports. Hidering factors include the COVID-19 pandemic and closure of NTCs
Financial management | Execution rates (global / Grants agreements) | - | - | - | - | [5 empty] | FY ongoing | 65% | 66% | 69% | 60% | 67% | 65.4% | The data is for grants agreements and the data source was the Grants financial reports FY 2017-2018 | 100% | 92% | 97% | 96% | 103% | 97.6% | The data is for grants agreements and the data source was the Grants financial reports FY 2018-2019 | 97% | 97% | 82% | 72% | 70% | 83.6% | 90% | NTC financial reports | Annually | Financial team | No cost | Implementation affected by lock down due to COVID-19. The data is for grants agreements and the data source was the Grants financial reports FY 2019-2020
[12 empty] | Global | [5 empty] | The data is for the Governing council budget line of NTCs and the data source was the Grants financial reports FY 2017-2019 | Global | [12 empty] | 90% | NTC financial reports | Annually | Financial team | No cost
Financial management | % of rejected expenditures | - | - | - | - | [5 empty] | Fisrt finacial report not yet approved | 1% | 1% | 11% | 1% | 0% | 2.8% | Data source was the Grants financial reports FY 2017-2018 | 0% | 3% | 1% | 1% | 3% | 1.6% | The data is for grants agreements and the data source was the Grants financial reports FY 2018-2019 | 0% | 0% | 0% | 7% | 0% | 1.4% | Less than 5% | NTC financial reports | Annually | Financial team | No cost | Non compliance with grant agreement on procurement guidelines.
Safe Learning Environment | Number of NTCs integrating violence/SLE in their annual action and budget plan | Plans developed for Fiscal Year 2017/18 | 0 | 0 | 0 | [5 empty] | 5 | 1 | 1 | 1 | 1 | 1 | 5 | An indicator on SLE is in the 5 NTCs' workplans: Activities promoting safe learning organised | 1 | 1 | 1 | 1 | 1 | 5 | Several activities were conducted on SLE as included in the NTCs work plan; SLE workshops conducted to disseminate findings of the GBV study in all colleges | 1 | 1 | 1 | 1 | 1 | 5 | 5 | NTC annual plan | Annual | M&E team | No cost | Several activities were conducted on SLE as included in the NTCs work plan
Output Area 1.3: TIET strengthened
Capacity development | SDHR: Overall performance score given by TIET members during organizational self-assessment exercise | 2,6 (on a scale from 1-4) | [8 empty] | SDHR self assessment not updated | [5 empty] | To be conducted during final year of SDHR project |  | n/a |  |  |  |  | 3.03 | Data was provided by SDHR | n/a | [5 empty] | 3.0 | Project data | Annually | ID team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Capacity development | % of implementation of TIET training plan | 0% | 0% | 0% | 0% | [5 empty] | 8% | [5 empty] | 54% | Data was provided by SDHR | n/a |  |  |  |  | 85% | Data was provided by SDHR | n/a | [5 empty] | 100% | TIET Progress reports | Annually | ID team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Operational management | Number of quarterly reviews for TIET | No formal monitoring mechanism | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 4 | The 4 expected quarterly reviews were conducted by the TIET department | 4 |  |  |  |  | 4 | The 4 expected quarterly reviews were conducted by the TIET department in 2019 | [5 empty] | 3 | 4 | TIET Progress reports | Annually | ID team | No cost | 3 out 4 expected quarterly reviews were conducted by the TIET department in 2020
TIET’s vision for policy design | Availability of a long term strategic plan for Teacher Training in Uganda | 0 | [8 empty] | 0 | [5 empty] | 0 | To be conducted during final year of project | n/a |  |  |  |  | To be conducted during final year of project | 1 draft to be validated in 2020 | 0 |  |  |  |  | 1 | 1 | Policy document | End of the project | ID team | No cost | The strategic plan was validated by M&E working group of MOES. TIET is currently extracting activities to done in 2021.
TIET as pilot of the whole teacher training system | Integrated monitoring system in place for PTE and ITE | 0 | [8 empty] | 0 | [5 empty] | 0 | To be conducted during final year of project | n/a |  |  |  |  | To be conducted during final year of project | To be conducted during final year of project | 0 |  |  |  |  | 0 | 2 | TIET Progress reports | End of the project | ID team | No cost | Not yet fully harmonized and also delyed due to factors like the COVID-19 pandemic
Output Area 1.4: CMU and PDU strengthened
Guidelines for sustainable infrastructures | Number of guidelines disseminated | 0 | [8 empty] | 0 | [5 empty] | 0 | The document is under development | n/a |  |  |  |  | 0 | The document is under development | n/a |  |  |  |  | 1 | 1per priority areas | CMU report | Annually | ID and Infra team | No cost | Manifesto for Climate Responsive Design were disseminated.
Capacity development | SDHR: Overall performance score given by CMU members during organizational self-assessment exercise | 1.4 (on a scale from 1-4) | [8 empty] | SDHR self assessmnet not updated | [5 empty] | To be conducted during final year of SDHR project |  | n/a |  |  |  |  | 2.1 | Data was provided by SDHR | n/a | [5 empty] | 3.0 | CMU report | Mid-term + Final evaluation report | ID and Infra team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Capacity development | % of implementation of CMU training plan | 0% | 0% | 0% | 0% | [5 empty] | 15% | [5 empty] | 56% | The data was provided by SDHR | n/a |  |  |  |  | 56% | There were no trainings conducted in 2019 | n/a | [5 empty] | 100% | CMU report | Annually (cumulative) | ID and Infra team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Efficiency of the service delivery | Level of timeliness of the procurements done by PDU | Criteria to be defined during baseline study | [8 empty] | baseline study not accepted by beneficiary | [5 empty] | baseline study not accepted by beneficiary |  | n/a |  |  |  |  | baseline study not accepted by beneficiary |  | n/a | [5 empty] | Criteria to be defined after baseline study | Baseline + End of project studies | End of the project | ID team | 10 000 € | baseline study not accepted by beneficiary. There were no trainings conducted in 2020; SDHR Project closed
Capacity development | SDHR: Overall performance score given by PDU members during organizational self-assessment exercise | 1,4 (on a scale from 1-4) | [8 empty] | SDHR self assessmnet not updated | [5 empty] | To be conducted during final year of SDHR project |  | n/a |  |  |  |  | 2.98 | Data was provided by SDHR | n/a | [5 empty] | 3.0 | PDU report | Mid-term + Final evaluation report | ID and Infra team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Capacity development | % of implementation of PDU training plan | 0% | 0% | 0% | 0% | [5 empty] | 0% | [5 empty] | 70% | The data was provided by SDHR | n/a |  |  |  |  | 70% | There were no trainings conducted in 2019 | n/a | [5 empty] | 100% | PDU report | Annually | ID and Infra team | No cost | There were no trainings conducted in 2020; SDHR Project closed
Output Area 2: Improved access to quality (sustainable) training and learning environment and facilities
Access to quality training and learning facilities | Number of infrastructure constructed according to benchmarked standards of the sustainable and renewable energy designs | 0 dormitories 0 training facilities | 0 dormitories 0 training facilities | 0 dormitories 0 training facilities | 0 dormitories 0 training facilities | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 4 | 6 | 1 | 16 | - | 27 | This is physical infrastructure progress | 4 | 24 | 7 | 22 | 1 | 58 | 4 | Progress reports on implementation of master plan | Annually | Infra Team | No cost | This is physical infrastructure progress. We have considered an average of 5 colleges because we included Unyama Early Child wood Development Centre was done there under Kaliro budget, even though intially it was not part of the original scope
Maintenance of training and learning facilities | Number of NTCs with operational maintenance and assets management plan in place | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | The maintenance plans are still under development | 1 | 1 | 1 | 1 | 1 | 1 | Based on TFF Muni; Masterplan done / budgets annually done / operational decision model data being gathered / awareness trainings ongoing / training staff ongoing / | 1 | 1 | 1 | 1 | 1 | 1 | 5 | Data from maintenance system NTC facilities | Annually | ID and Infra team | No cost | Masterplan done / budgets annually done / operational decision model data being gathered / awareness trainings ongoing / training staff ongoing /
Output Area 3: Pedagogical approaches to pre- and in-service teacher training effectively applied at NTC and in partner schools.
Strengthened pedagogical support | Average satisfaction of female and male academic staff with the amount and quality of pedagogical support provided by KYU (on a scale from 1 to 4) |  |  |  |  | 2.8 (3 F,2.6 M) | 2.25 (2.3 F,2.2M) | 2.7 (2.6 F,2.8M) | 2.55 (2.8 F,2.3 M) | 2.5 (2.8 F,2.2 M) | 2.5 | [5 empty] | To be conducted in 2019 |  | 2.5 (2.2 F, 2.8 M) | 1.7 (1.0 F, 2.3 M) | 2.4 (1.5 F, 3.3 M) | 2.6 (2.9 F, 2.2 M) | 2.3 (2.0 F, 2.5 M) | 2.3 (1.9 F, 2.6 M) | The source of the data was the pedagogy survey results; self delaration by NTC lecturers in the 5 NTCs (August 19, Questionnaires were used for data collection). | 2.3 (2.3F, 2.2M) | 1.9 (1.5F, 2.0M) | 2.3 (2.9F, 2.1M) | 1.8 (1.0F, 1.9M) | 2.2 (2.2F, 2.2M) | 2.1 | 3 | Project survey data | Mid-term + end of project | Peda team | 8,000 EUR | The source of the data was the survey results (December 2020, Questionnaires were used for data collection).
Strengthened pedagogical support | Average satisfaction of female and male pedagogic staff with the amount and quality of support provided by mentors in the NTCs (mentorship system) (on a scale from 1 to 4) |  |  |  |  | 2.85 (F 2.9, M 2.8) | 2.25 (2.1 F,2.4M) | 2.9 (2.8 F,3 M) | 3.05 (2.9,3.2) | 2.7 (2.8,2.6) | 2.7 | [5 empty] | To be conducted in 2019 |  | 3.1 (3.1 F, 3.0 M) | 2.8 (2.8 F, 2.8 M) | 3.7 (4.0 F, 3.3 M) | 2.9 (3.3 F, 2.4 M) | 2.5 (2.6 F, 2.4 M) | 3.0 (3.2 F, 2.8 M) | The source of the data was the pedagogy survey results; self delaration by NTC lecturers in the 5 NTCs (August 19, Questionnaires were used for data collection). | 2.8 (3.1F, 2.6M) | 2.4 (1.9F, 2.5M) | 2.5 (2.7F, 2.4M) | 2.9 (2.9F, 2.8M) | 2.5 (2.6F, 2.4M) | 2.6 | 3 | Project survey data | Mid-term + end of project | Peda team | 8,000 EUR | The source of the data was the survey results (December 2020, Questionnaires were used for data collection).
Strengthened professional competencies of NTC academic staff | Average satifaction expressed by pedagogic staff (F/M) following Continuous Professional Development activities (professional development modules, support supervision system, training…) (on a scale from 1 to 4) |  |  |  |  | 2.85 (2.8 F, 2.9 M) | 2.4 (2.2 F, 2.6 M) | 2.95 (2.9 F, 3M) | 3.15 (3.1 F, 3.2 M) | 2.75 (2.8 F,2.7M) | 2.8 | [5 empty] | To be conducted in 2019 |  | 3 (3.0 F, 2.9 M) | 2.5 (2.5 F, 2.5 M) | 3.2 (3.0 F, 3.3 M) | 2.9 (3.2 F, 2.5 M) | 2.6 (2.7 F, 2.5M) | 2.8 (2.9 F, 2.7 M) | The source of the data was the pedagogy survey results; self delaration by NTC lecturers in the 5 NTCs (August 19, Questionnaires were used for data collection). | 2.5 (2.8F, 2.3M) | 2.6 (2.8F, 2.5M) | 2.7 (3.0F, 2.7M) | 2.9 (2.9F, 2.9M) | 2.4 (2.6F, 2.2M) | 2.6 | 3 | Project survey data CPD reports | Mid-term + end of project | Peda team NTC | No cost | The source of the data was the survey results (December 2020, Questionnaires were used for data collection).
Increased access to information and pedagogical content | Average satisfaction of female and male pedagogical staff regarding the libraries and ICT facilities (on a scale from 1 to 4) |  |  |  |  | 2.3 (2.5 F, 2.1M) | 2.65 (2.6 F, 2.7M) | 2.25 (2.3 F, 2.2 M) | 2.7 (2.5 F, 2.9 M) | 2.8 (2.8 F,2.8 M) | 2.5 | [5 empty] | To be conducted in 2019 |  | 2.5 (2.4F, 2.5M) | 2.6 (2.6F, 2.6M) | 2.2 (2.1F, 2.2M) | 2.7 (2.8F, 2.6M) | 2.8 (2.7F, 2.8M) | 2.5 (2.5F, 2.5M) | The source of the data was the pedagogy survey results; self delaration by NTC lecturers in the 5 NTCs (August 19, Questionnaires were used for data collection). | 3.4 | 3.3 | 3 | 3.3 | 3.2 | 3.2 | 3 | Project survey data | Mid-term + end of project | Peda team | No cost | The source of the data was the Tracer study on E-learning Readiness. The survey was conducted by IPSOS (Nov-Dec 2020, Questionnaires/interviews/FGDs were used for data collection).
Increased access to information and pedagogical content | Average satisfaction of female and male students regarding the libraries and ICT facilities (on a scale from 1 to 4) | To be collected | To be collected | To be collected | To be collected | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | To be collected in Feb 18 | 2.8 | 2.8 | 2.1 | 2.5 | 2.9 | 2.6 |  | 2.8 (2.8F, 2.8M) | 3.0 (3F, 2.9M) | 2.6 (2.5F, 2.6M) | 2.8 (2.8F, 2.7M) | 3.0 (3F, 2.9M) | 2.8 (2.8F, 2.8M) | The source of the data was the pedagogy survey results; self delaration by NTC students in the 5 NTCs (August 19, Questionnaires were used for data collection). | 3 | 3 | 2.6 | 2.9 | 2.9 | 2.8 | 3 | Project survey data | Mid-term + end of project | Peda team NTC librarians | No cost | The source of the data was the survey results (December 2020, Questionnaires were used for data collection).
Increased access to information and pedagogical content | Level of application by lecturers of ICT in teaching and learning (on a scale from 1 to 4) |  |  |  |  | 2.27 (2.05 F, 2.5 M) | 2.85 (2.8 F, 2.9 M) | 2.9 (2.7 F, 3.1M) | 2.97 (2.6 F, 3.35 M) | 2.5 (2.5 F,2.5 M) | 2.7 | 3 | 2.1 | 2.5 | 3.3 | 2.1 | 2.6 |  | 2.7 (2.8F, 2.5M) | 3.1 (3.3F, 2.9M) | 3.4 (3.3F, 3.4M) | 2.8 (2.8F, 2.7M) | 2.7 (3.1F, 2.3M) | 2.9 (3.1F, 2.8M) | The source of the data was the pedagogy survey results; self delaration by NTC lecturers in the 5 NTCs (August 19, Questionnaires were used for data collection). | 3.9 | 3.8 | 3.9 | 3.8 | 3.6 | 3.8 | 2.5 | Classroom observation tool Project survey | Annually | NTC mentors | No cost | The source of the data was the Tracer study on E-learning Readiness. The survey was conducted by IPSOS (Nov-Dec 2020, Questionnaires/interviews/FGDs were used for data collection).
School practice turned into a learning tool | Level of application by NTC students of ATL in continuous school practice (on a scale from 1 to 4) | 0,0 | 0,0 | 0,0 | 0,0 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | 3.2, 3.3 | 3.1, 3.1 | 3.3, 3.2 | 3.3, 3.4 | 3, 3.1 | 3.2 |  | 3.1 (M=3.1, F=3.1) | 2.8 (M=2.8, F=2.6) | 3.0 (M=2.9, F=3.0) | 3.2 (M=3.2, F=3.2) | 2.9 (M=3.0, F=2.7) | 3 (M=3.0, F=2.9) | Data source will be the ATL/ICT monitoring tool results. Observations were conducted for DES yr.2 students by lecturers during Microteaching sessions (Nov, 2019). | Not possibble to collect due to the effect of the COVID-19 Pandemic and school institutions being closed | [5 empty] | 2.5 | Classroom observation tool Site Visit continuous school practice reports | Annually | School practice officer | No cost
School practice turned into a learning tool | % of DES students (M/F) doing CSP activities in the NTC and in the partner secondary schools | 0,0 | 0,0 | 0,0 | 0,0 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | To be collected in 2018 | 100% | 54% | 67% |  | 50% | 67.75% |  | 50% | 59% | 99% | 71% | 94% | 74.6% | Data was provided by school practice officers; DES yr.1s of acdemic year 2018/2019_Data source was the PSS evaluation report | Not possibble to collect due to the effect of the COVID-19 Pandemic and school institutions being closed | [5 empty] | 75% | Continuous school practice reports | Annually | School practice officer | No cost
Partner secondary schools strengthened | Level of application by secondary school teachers of ATL (on a scale from 1 to 4) | To be collected | To be collected | To be collected | To be collected | 2.8 | 3 | 2.8 | 2.7 |  | 2.7 | [5 empty] | To be conducted in 2019 |  | 3.0 (3F, 3M) | 2.6 (2.7F, 2.6M) | 2.9 (3F, 2.9M) | 3.1 (3.2F, 3M) | 3.0 (3F, 3M) | 2.9 (2.9F, 2.9M) | Data collection method was class pbservations that done by mentors in PSS in July 2019 using the ATL/ICT monitoring tool | Not possibble to collect due to the effect of the COVID-19 Pandemic and school institutions being closed | [5 empty] | 2.5 | Classroom observation tool Site Visit Pre and post test | Annually | NTC mentors | No cost | -
Partner secondary schools strengthened | % of partner secondary schools trained in violence prevention and response | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 1 mission to PSS was conducted together with TIET/SE/Enabel in June 2019. Report was submitted and action points are being implemented. | - | - | - | - | - | - | 80% | Training reports | Annually | Peda team | No cost | No trainings were conducted in 2020
Pedagogical activities supported | Number of DES students submitting personal projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | n/a | [5 empty] | This was one of the areas that the project was advised to cancel out after the Mid term evaluation and to put emphasis on those that are already ongoing. | n/a | [5 empty] | increasing number from year to year | NTC reports | Annually | Peda team | No cost | This was one of the areas that the project was advised to cancel out after the Mid term evaluation and to put emphasis on those that are already ongoing.
Pedagogical activities supported | Number of lecturers developing /publicating researches (action or academic) | 1 | 0 | 15 | 0 | 0 | 1 | 19 | 3 | 0 | 23 | 2 (0F,2M) | 28 (6 F, 22 M) | 12 (3F, 9M) | 29 (7F, 22M) | 8 (4F, 4F) | 79 (20F, 59M) |  | 2 (2M) | 12 (5F, 7M) | 10 (2F, 8M) | 19 (7F, 12M)+ 6 for academic research | 7 (5F, 2M) | 50 (19F, 31M)+ 6= 56 | Results are those of lecturers that developed action research reports in 2019. | - | - | - | - | - | - | increasing number from year to year | NTC CPD reports | Annually | Peda team NTC | No cost | No lecturers developed or published researches
Note on Q1: Windows User:
Note on B7: Personal: Sounds like two indicators: Extent of joining training institutions, and proportion of those who indicate to have been able to apply their teaching skills
Note on C7: Personal: Baseline data?
Note on L8: Nie: Annual Performance report FY 2016-17, exams 2016
Note on C11: Personal: Baseline data?
Note on G11: Nie: Data includes the students who did repeat the exam; explaining why it is 106%
Note on M11: Nie: Data includes the students who did repeat the exam; explaining why it is 106%
Note on C12: Personal: Are there any disintegrated mechanisms in place?
Note on AH12: Personal: Observation of work-plan copies
Note on C15: Personal: Baseline data?
Note on B17: BTCCTB: Meetings(committee, mgt, Qtr review & data analysis wkshop)
Note on B20: BTCCTB: SDHR
Note on B21: BTCCTB: SDHR
Note on B22: BTCCTB: data from grant agreement(2017/2018) Activities related to capacity development plan (B.7.1)
Note on B23: Personal: Indicator is not clear
Note on B27: BTCCTB: Grant agreement to be considered
Note on B29: BTCCTB: get from philip- grant agreemt
Note on B32: BTCCTB: review kaliro TFF
Note on C32: Personal: Don't understand 2,6
Note on B33: BTCCTB: from SDHR
Note on B34: BTCCTB: inquire from Abdul
Note on B40: BTCCTB: SDHR
Note on B43: BTCCTB: SDHR
Note on B46: BTCCTB: discuss with Nobert
Note on B48: BTCCTB: planned for 2019
Note on B49: BTCCTB: for 2019
Note on B50: BTCCTB: for 2019
Note on B51: BTCCTB: for 2019
Note on L53: Nie: Survey declaration: I use ICT for preparing my lessons, I use ICT into my lessons as a resource tool for all students
Note on B56: Personal: Data to be collected by mentors
Note on G56: Personal: Data at the end of 2017 here is based on post-test scores for ATL training.
Note on C59: Nie: Baseline: NTC RBM review October 2017
Note on D59: Nie: Baseline: NTC RBM review October 2017
Note on E59: Nie: Baseline: NTC RBM review October 2017
Note on F59: Nie: Baseline: NTC RBM review October 2017

## Grants (hidden)
Result | Indicator/Progress Marker | Baseline Muni | Baseline Kaliro | Baseline Mubende | Baseline Kabale | Data end of 2017 | [5 empty] | Data for end of 2018 | [5 empty] | Data for end of 2019 | [5 empty] | Target (2020) | Source/ Means of Verification | Frequency | Resp. person | Budget | Comments on 2019 data | Remarks
[6 empty] | Kabale | Kaliro | Mubende | Muni | Unyama | Average | Kabale | Kaliro | Mubende | Muni | Unyama | Average/Total | Kabale | Kaliro | Mubende | Muni | Unyama | Average/Total
Capacity development | % of implementation of NTCs capacity development plans | Plans developed in September 2017 | [8 empty] | FY ongoing | 0% | 29% | 0% | 85% | 30% | 28.8% | [6 empty] | 80% | NTC Progress reports , (Grant agreement) | Annually | ID team | No cost | Data source was the Grants financial reports FY 2017-2018
Financial management | Execution rates (global / Grants agreements) | - | - | - | - | [5 empty] | FY ongoing | 65% | 66% | 69% | 60% | 67% | 65.4% | [6 empty] | 90% | NTC financial reports | Annually | Financial team | No cost | The data is for grants agreements and the data source was the Grants financial reports FY 2017-2018
[12 empty] | Global | [5 empty] | Global | [5 empty] | 190% | NTC financial reports | Annually | Financial team | No cost | The data is for the Governing council budget line of NTCs and the data source was the Grants financial reports FY 2017-2019
Financial management | % of rejected expenditures | - | - | - | - | [5 empty] | Fisrt finacial report not yet approved | 1% | 1% | 11% | 1% | 0% | 2.8% | [6 empty] | Less than 5% | NTC financial reports | Annually | Financial team | No cost | Data source was the Grants financial reports FY 2017-2018
Note on B4: BTCCTB: data from grant agreement(2017/2018) Activities related to capacity development plan (B.7.1)
Note on B5: BTCCTB: Grant agreement to be considered
Note on B7: BTCCTB: get from philip- grant agreemt

## Sheet1 (hidden)
| No. of indicators | 2018 expected results | Data results got so far
ID | 21 | 14 | 7
Infrastructure | 3 | 1 | 1
Pedagogy | 13 | 6 | 4