## Rwanda
ANNEX 5B: Rwanda Logframe
Title of the action | Enhancing community resilience to epidemics and hydro-meteorological hazards in the African Great Lakes region
Main objective | Save lives, reduce suffering, preserve of human dignity of people vulnerable to epidemics and hydro-meteorological hazards and epidemics in Rwanda
| Intervention logic | Objectively verifiable indicators | Baseline value | Target value | Achieved at Interim report | Achieved at final report | Total final achievement in % | Comments
Specific objective | Reduced mortality and morbidity within communities affected by infectious disease outbreaks and HM hazards through enhancing community-based prevention, mitigation, early-warning and early-response
Outcome 1 | Improved ability of targeted communities to adopt positive health and hygiene practices. | % of respondents who correctly identified 3 key health & hygiene risks and 3 key health & hygiene practices (related to AWD and Ebola) in targeted communities | To be determined | 65% |  | 65.5% | 100.8% | * 65.5% on hygiene related diseases * 77.3% for Covid19 prevention
Output 1.1 | Volunteers trained in CBHFA, especially hygiene promotion through CBHEPP/CBHFA/RANAS | Number of volunteers within target area trained in CBHEPP/CBHFA/RANAS | 0 | 95 | 11 | 93 | 97.89% | * ToT eCBHFA in March 2020: 11 * Training eCBHFA in August 2020: 21 * Training eCBHFA April 2021: 36 * refresher training November 2021: 25 The initial target for this indicator was to train 95 volunteers. To increase the coverage of these trainings it was decided not to only focus on volunteers but also include health workers. Next to the 93 volunteers there are 21 healthcare workers and 5 branch coordinators and focal points trained in these topics, who are not considered as volunteers and therefore not included in this indicator.
Output 1.2 | Volunteers conduct CBHEPP/CBHFA/RANAS hygiene promotion sessions in targeted communities | Number of households reached through CBHEPP/CBHFA/RANAS hygiene promotion session during household visits | 0 | 1500 | 2650 | 2650 | 176.7% | * HH visits November 2019: 2650 * Hygiene clubs: 554 (were also already targeted during HH visits in November 2019)
Output 1.3 | Selected community members receive health and hygiene promotion supplies | Number of health and hygiene promotion supplies procured and distributed to community members | 0 | 280 (sets) | 0 | 280 | 100%
Activities Outcome 1
Activity 1.1 | Conduct Trainer of trainers for CBHFA facilitators
Activity 1.2 | Conduct training of volunteers and community health workers on core CBHFA modules
Activity 1.3 | Conduct CEA training for volunteers (mobile cinema, radio show)
Activity 1.4 | Organize a yearly refresher for CBHFA volunteers
Activity 1.5 | Border sensitization sessions using language adapted means (20 wall painting)
Activity 1.6 | Development of sector risk maps for specific health risks
Activity 1.7 | Setting up and facilitating hygiene clubs in the targeted communities
Activity 1.8 | Organising interactive awareness raising sessions on CBHFA using 24 mobile cinema shows and 8 radio shows
Activity 1.9 | Trained volunteers conduct house to house visits (incentives)
Outcome 2 | Improved ability of RRCS to prevent, detect and respond to disease outbreaks at the community level in the targeted districts | Total amount of people reached through awareness raising campaignes | 0 | 500000 | 1052600 | 4508856 | 901.8% | * mobilization sessions Ngororero (March-April 2020): 18.000 people * sessions Rubavu (March -April 2020): 34.600 people * 4 radio shows Rubavu 2020: 1.000.000 people * Mobilisation sessions 2021/2022: 4.508.856 The total amount of people reached through awareness raising sessions is a lot higher than initially forseeen (902%). At the moment of establising the target of 500.000, the full impact of the Covid-19 impact was not yet clear. Sensitisation sessions continues in 2021 and even in 2022 which was initially difficult to foreseen.
Output 2.1 | RRCS staff and volunteers trained and equipped to perform COVID-19 activities in targeted communities. | Number of staff and volunteers trained and equiped for COVID-19 preparedness and response | 0 | 300 (10 volunteers per district x 30 districts) | 0 | 503 | 167.7% | * Phase 1: 20 participants(NDRT/BDRT and RRC staff) * Phase 2: 483 BDRT and LDRT from 416 sectors in 30 districts The total amount of staff and volunteers trained is higher than initially foreseen (168%). At the moment of establising the target of 300 it was estimated on 10 volunteers per district. In a later stage it was decided by RRC to target at least one volunteer per sector (416).
Output 2.2 | RRCS staff and volunteers conduct COVID-19 activities in targeted communities | Number of awareness raising campaignes organized | 0 | 130 | 21 | 305 | 234.6% | * 6 mobilization sessions Ngororero (March-April 2020) * 11 sessions Rubavu (March -April 2020) * 4 radio shows Rubavu 2020 * Mobilisation sessions 2021/2022: 284 The total number of awareness raising sessions is a lot higher than initially forseeen (235%). At the moment of establising the target of 130, the full impact of the Covid-19 impact was not yet clear. Sensitisation sessions continues in 2021 and even in 2022 which was initially difficult to foreseen.
Activities Outcome 2
Activity 2.1 | Conduct training on PSS for the teams involved in the response to disease outbreaks
Activity 2.2 | Establish a technical response working group on infectious diseases within the RRC at HQ level
Activity 2.3 | Conduct an advanced KOBO collect training to at HQ level
Activity 2.4 | *NEW* Training of NDRT volunteers and staff on COVID-19
Activity 2.5 | *NEW* Risk Communication, tracking and management of rumors related to COVID-19 (production of radio shows, procurement of radio show material, radio dissemination, TV shows, social media adverts, short videos, songs, and conducting radio show)
Activity 2.6 | *NEW* Development of IEC tools/materials COVID-19
Activity 2.7 | *NEW* Dissemination of COVID-19 IEC materials and messages (via radio,FABL app, …)
Activity 2.8 | *NEW* Procurement and distribution of protective equipment COVID-19
Activity 2.9 | *NEW* Procurement and distribution of WASH facilities for COVID-19
Activity 2.10 | *NEW* Volunteer protection/insurances COVID-19
Activity 2.11 | *NEW* Crisis modifier for health emergencies - COVID 19 (relief items, food assistance or MPCT for the most vulnerable families affected by COVID-19 outbreak)
Activity 2.12 | Running Emergency Medical Services
Outcome 3 | Improved resilience of communities living in high risk areas and strengthened institutional capacity of the RRCS and other stakeholders to respond to HM disasters | Number of emergency committee members / members of volunteer groups in the project area showing skills in carrying relevant response tasks according to minimum standards in a coordinated manner | 0 | 280 | 0 | 318 | 113.6% | 318 out of 336 community risk committee members trained in April 2021.
Output 3.1 | Community risk management committees trained in disaster risk management. | number of trained Community Risk Management committees | 0 | 28 | 0 | 28 | 100% | 28 committees trained in April 2021 (9 in Rubavu, 9 in Ngororero and 10 in Rutsiro).
Output 3.2 | Communities sensitized on climate change and disaster risk reduction at community level. | Number of community sensitization sessions held | 0 | 534 | 12 | 1844 | 345.3% | * HH visits in 2019: in Ngororero (6 villages) and Rutsiro (6 villages) * DRR sessions in schools: 168 * 1.664 sensitisation sessions The total number of community sensitization sessions is higher than initially forseeen (345%).The sensitisation and awareness on Covid-19 increased the capacity of volunteers to organize these kind of sessions by using megaphones, motorbikes,. These equipments could also support the awareness on other topics such as climate change and disaster risk reduction.
Output 3.3 | Contingency plans and evacuation routes drafted by community. | number of contingency plans drafted | 0 | 31 | 0 | 30 | 96.77% | * Sector Contingency plans: 9 * District Contingency plan: 3 * DRR plans after eVCA: 18
Output 3.4 | Training of volunteers in DRR related topics | Amount of Red Cross volunteers trained in DRR-related topics | 0 | 90 | 45 | 120 | 133.3% | 3 BDRT trainings: * December 2019: 45 BDRT volunteers * August 2020: 45 BDRT volunteers * May 2021: 30 BDRT volunteers
Activities Outcome 3
Activity 3.1 | Train community risk management committees at sector level
Activity 3.2 | Organize regular meetings of the community risk management committees together with the RRC volunteers
Activity 3.3 | Organize information sessions for all stakeholders regarding the set-up of the risk management committees
Activity 3.4 | Organize an annual DRR awareness event on the international day for natural disaster risk reduction (13/10)
Activity 3.5 | Organize DRR sensitization sessions in schools using DRR booklets
Activity 3.6 | Organizing interactive awareness raising sessions on DRR in targeted villages using 348 mobile cinema and 12 radio shows
Activity 3.7 | Organizing awareness campaigns on DRR topics in targeted villages using wall paintings
Activity 3.8 | Conduct a VCA training on BDRT and NDRT level
Activity 3.9 | Draft a risk map and contingency plan per sector where none is yet available
Activity 3.10 | Draft a risk map and contingency plan per district where none is yet available
Activity 3.11 | Organize volunteer meetings at sector level
Activity 3.12 | Support DRR related community activities
Activity 3.13 | Conduct a BDRT training in each branch
Activity 3.14 | Conduct a cash training for selected volunteers within the BDRT teams
Outcome 4 | Improved Early Warning (EW) systems at community level leading to a more targeted and effective Early Response prior to the HM disaster or thereafter | Number of community members in the project area who receive early warning messages in a timely manner from at least one source | 0 | 191857 | 0 | 58325 | 30.4% | Since government institutions of Rwanda, such as MINEMA, demand a national early warning system, implementation requires coordination from them, which have caused some delays in the roll out of EWS as planned within this DPIII project. This postponement is exacerbated by the current COVID-19 pandemic which affects the whole project. Together with the fact that there is complementarity between RRCS and the World bank for the implementation of an early warning system in the Sebeya catchment, wherefore the World bank can provide funds, it was decided to reduce the implementation and funding for the early warning systems under result 4 within this project. Therefore the achieved indicators were less than initially targeted.
Output 4.1 | Operational early warning systems are set up at community level. | Number of operational EWS that are understood by target operation | 0 | 28 | 0 | 0 | 0%
Output 4.2 | Community EW integrated into national/regional EW systems | Number of community EWS integrated into national/regional EWS | 0 | 28 | 0 | 14 | 50%
Output 4.3 | Assistance provided in coordination with the authorities following a natural disaster through a crisis modifier | Amount of people that received in-kind/cash assistance by the project | 0 | 4600 | 5115 | 7300 | 158.7% | * April/May 2020: 5115 people supported with NFI's in Ngororero district * August 2020: 1600 people supported with cash distribution in Ruhango/Rulindo district * May 2021: 585 people supported with cash distribution in Nyamesheke district More people received support with the crisis modifier than initially foreseen because more funds became available due to different modification requests.
Comment
Activities Outcome 4
Activity 4.1 | Organize a training at branch level regarding early warning, early action
Activity 4.2 | Identify and validate the most adequate early-warning systems per community
Activity 4.3 | Set up the early warning protocols with the different stakeholders.
Activity 4.4 | Sign an agreement with several mobile communication companies for country wide coverage of the early warning messages
Activity 4.5 | Organize a pilot case in a specific district and test-run the service during a simulation and/or real-time interventions
Activity 4.6 | Organize a lessons-learned workshop on the results of the pilot case
Activity 4.7 | Cash grant (crisis modifier)

## Tanzania
ANNEX 5C: Tanzania Logframe
Title of the action | Enhancing community resilience to epidemics and hydro-meteorological hazards in the African Great Lakes region
Main objective | Save lives, reduce suffering, preserve of human dignity of people vulnerable to, hydro-meteorological hazards, epidemics and protracted crisis in Tanzania
| Intervention logic | Objectively verifiable indicators | Baseline value | Target value | Achieved at Interim report | Achieved at final report | Total final achievement in % | Comments
Specific objective | Reduced mortality and morbidity within communities affected by infectious disease outbreaks and HM hazards through enhancing community-based prevention, mitigation, early-warning and early-response
Outcome 1 | Improved ability of targeted communities to adopt positive health and hygiene practices. | Amount of volunteers & staff trained in CBHFA | To be determined | 3000% | 37 | 0 | 37%
Output 1.1 | Volunteers trained in CBHFA, especially hygiene promotion | Number of volunteers within target area trained in CBHFA | 0 | 100 | 37 | 0 | 37% | There were no further trainings nor activities conducted on CBHFA after the interim report period hence low target numbers achieved at the end
Activities Outcome 1
Activity 1.1 | Conduct Trainer of trainers for CBHFA facilitators
Activity 1.3 | Development of village risk maps for specific health risks
Outcome 2 | Improved ability of TRCS to prevent, detect and respond to disease outbreaks at the community level in the targeted districts | Total amount of people reached through awareness raising campaignes | 0 | 200000 | 8728915 | 18321 | 4374%
Output 2.1 | TRCS staff and volunteers trained and equipped to perform COVID-19 activities in targeted communities. | Number of staff and volunteers trained and equiped for COVID-19 preparedness and response | 0 | 1050 | 415 | 10 | 40.48% | Reported only those targeted by the project
Output 2.2 | TRCS staff and volunteers conduct COVID-19 activities in targeted communities | Number of awareness raising campaignes organized | 0 | 4000 | 415 | 10 | 10.62% | Reported only those targeted by the project
Activities Outcome 2
Activity 2.1 | *NEW* COVID-19 induction training to TRCS staff and volunteers
Activity 2.2 | *NEW* Training of community based volunteers in 10 high risk regions covering COVID-19 RCCE sensitization and distribution and dissemination of IEC materials to the communities
Activity 2.3 | *NEW* Risk communication and community engagement activities COVID-19 in urban settings
Activity 2.4 | *NEW* Risk communication and community engagement activities COVID-19 in rural settings
Activity 2.5 | *NEW* Procurement of personal protective equipment COVID-19
Activity 2.6 | *NEW* Procurement of public awareness raising equipment COVID-19
Activity 2.7 | *NEW* Crisis modifier for health emergencies - COVID 19 (relief items, food assistance or MPCT for the most vulnerable families affected by COVID-19 outbreak)
Outcome 3 | Improved resilience of communities living in high risk area of the Mbeya region and strengthened institutional capacity of the TRCS and other stakeholders to respond to Hydrometeriological disasters and protracted crisis | Number of emergency committee members / members of volunteer groups in the project area showing skills in carrying relevant response tasks according to minimum standards in a coordinated manner | 0 | 50 | 0 | 31 | 62% | Knowledge tested during simulation exercise
Output 3.1 | Community risk management committees trained in disaster risk management. | number of trained Community Risk Management committees | 0 | 5 | 0 | 5 | 100%
Output 3.2 | Communities sensitized on climate change and disaster risk reduction at community level. | Number of community sensitization sessions held | 0 | 144 | 1 | 36 | 25.69% | Only two sessions were conducted per village i.e 18 villages*2 sessions.
Output 3.3 | Contingency plans and evacuation routes drafted by community. | number of contingency plans drafted, number of evacuation routes signposted | 0 | 18 | 0 | 1 | 5.556% | . Response plans were developed in the 18 targeted villages . Only one district based contingency plan was developed for the target district
Output 3.4 | Training of volunteers in DRR related topics | Amount of Red Cross volunteers trained in DRR-related topics | 0 | 100 | 27 | 26 | 53%
Activities Outcome 3
Activity 3.1 | Train community risk management committees at village level
Activity 3.2 | Organize an annual DRR awareness event on the international day for natural disaster risk reduction (13/10)
Activity 3.4 | Organizing interactive awareness raising sessions on DRR in targeted villages using mobile cinema and radio shows
Activity 3.5 | Conduct a VCA TOT training on BDRT and NDRT level
Activity 3.6 | Perform a risk map per village where no risk map is yet available
Activity 3.7 | Perform a risk map per ward where no risk map is yet available
Activity 3.8 | Perform a risk map per district where no risk map is yet available
Activity 3.9 | Draft or update the contingency plan at village level
Activity 3.10 | Draft or update the contingency plan at ward level
Activity 3.11 | Draft or update the contingency plan at district level
Activity 3.12 | Identify and signpost safe evacuation routes
Activity 3.13 | Organize volunteer meetings at village level
Activity 3.15 | Train volunteers in FA
Outcome 4 | Improved Early Warning (EW) systems at community level leading to a more targeted and effective Early Response prior to the HM disaster or thereafter | Number of community members in the project area who receive early warning messages in a timely manner from at least one source | 0 | 30000 | 0 | 40490 | 135% | This is the population of the 5 wards where early warningsystems were installed
Output 4.1 | Operational early warning systems are set up at community level. | Number of operational EWS that are understood by target operation | 0 | 10 | 0 | 8 | 80%
Output 4.2 | Community EW integrated into national/regional EW systems | Number of community EWS integrated into national/regional EWS | 0 | 10 | 0 | 8 | 80%
Output 4.3 | Assistance provided in coordination with the authorities following a natural disaster through a crisis modifier | amount of people that received in-kind/cash assistance by the project | 0 | 1300 | 0 | 2250 | 173.1% | 2250 people provided with non food items prepositioned at TRCS warehouse in Dodoma
Activities Outcome 4
Activity 4.1 | Organize a training at branch level regarding early warning, early action
Activity 4.2 | Identify and validate the most adequate early-warning systems per community (community meeting)
Activity 4.3 | Set up early warning teams at community level
Activity 4.4 | Communication of early warning messages
Activity 4.5 | Set up the early warning protocols with the different stakeholders
Activity 4.6 | Organize a pilot case in a specific district and test-run the service during a simulation and/or real-time interventions
Activity 4.8 | Crisis modifier
Outcome 5 | Refugee and host communities in Nduta refugee camp have improved access to primary health care including comprehensive health care services, health education, sexual reporductive health, first aid and blood banking services. | Number of persons having access to primary health care services | 74,788 refugees and 11,218 host communities members | 74,788 refugees and 11,218 host communities members | NA | 65,350 refugees and 7,842 host communities members | 85.1%
Output 5.1 | Refugee population and host community have access to four well managed health posts for medical care | Number of consultations and laboratory diagnostic tests performed | 0 | 95% of the average number of monthly consultations and laboratory diagnostisc tests of 2020 | NA | 26747 | 100.3%
Output 5.2 | Community health care services are provided, including basic first aid services, nutrition and sexual and reproductive health outreaches | Number of outreach sessions held | 0 | 576 | NA | 634 | 110.1%
Output 5.3 | Blood donor recruitment campaigns are successfully undertaken | Number of blood donor recruitment campaigns conducted | 0 | 12 | NA | 13 | 108.3%
Activities Outcome 5
Activity 5.1 | Health education disemination
Activity 5.2 | Blood donor campaigns
Activity 5.3 | First Aid training and services
Activity 5.4 | Complementary/special diet for the people with medical conditions
Activity 5.5 | Support activities for people living with HIV
Activity 5.6 | Provision of comprehensive health care delivery
Activity 5.7 | Provision of laboratory diagnostic services
Activity 5.8 | Dispensing of drugs and supply chain management
Activity 5.9 | Referral of severely ill patients to Nduta Hospital
Activity 5.10 | Printing of patient medical records
Activity 5.11 | Provision of sexual and reproductive health services
Activity 5.12 | Training of the health post staff on drug management and rational prescription
Activity 5.13 | Training of the health post staff on malaria case management
Activity 5.14 | Training of the health post staff on integrity and compliance
Activity 5.15 | Training of the health post staff on SGBV and PSEA
Activity 5.16 | Supporting a complaints mechanism
Note on B11: lkibet: this activity was achieved indirectly when Outcome 3 activities were being implemented
Note on A28: Dries Goeminne: I'm confused, thought we were going to drop most of the classic activities, under outcome 3 and 4? Difficult for me to provide feedback here, without seeing the final budget modifications

## Uganda
ANNEX 5D: Uganda Logframe
Title of the action | Enhancing community resilience to epidemics and hydro-meteorological hazards in the African Great Lakes region
Main objective | Save lives, reduce suffering, preserve of human dignity of people vulnerable to epidemics and hydro-meteorological hazards and epidemics in Uganda
| Intervention logic | Objectively verifiable indicators | Basline value | Target value | Achieved at Interim report | Achieved at final report | Total final achievement in % | Comments
Specific objective | Reduced mortality and morbidity within communities affected by infectious disease outbreaks and HM hazards through enhancing community-based prevention, mitigation, early-warning and early-response
Outcome 1 | Improved ability of targeted communities to adopt positive health and hygiene practices. | % of respondents who correctly identified 3 key health & hygiene risks and 3 key health & hygiene practices (related to AWD and Ebola) in targeted communities | To be determined | 65% | 0% | 70.8% | 108.9% | The evaluation establihsed that 70% of the target beneficiries were reached with health and hygiene messages through this the action and we have used this as proxy indicator for indicator for this Outcome. Additionally 73% of the beneficries were reached through health and hygiene activities based on the progress reports
Output 1.1 | Volunteers trained in CBHFA, especially hygiene promotion through RANAS | Number of volunteers within target area trained in hygiene promotion | 0 | 100 | 0 | 100 | 100% | 100 volunteers were trained by 15 master trainers on integrated course combining both (eCBHFA) and Epidemic Control for Volunteers
Output 1.2 | Volunteers conduct hygiene promotion sessions in targeted communities | Number of households reached through hygiene promotion session during household visits | 0 | 2500 | 0 | 30401.6667 | 100% | A total of 30,402 unique household visits weree conducted reaching a population of 182410 persons. The target 2500 housholds were in the host community , however, the project supported the refugee population in Kikkube and Kyegewa giving the high number households reached due to population density in the refugee settlemnet
Output 1.3 | Selected community members receive health and hygiene promotion supplies | Number of health and hygiene promotion supplies procured and distributed to community members | 0 | 210 (sets) | 0 | 412 | 100% | The targeting, purchasing and distribution of health and hygiene improvement kits resulted in 100% achivement. Each cohort had specific needs and each of them had more that 210 members reached as illustraded below; > 412 expectant mothers in Kikuube and Kyegegwa received mama kits and Mosquito nets. > 495 adolescent girls & women of reproductive age registered from extremely vulnerable households in Kikuube and Kyegegwa district received complete set of Menstrual Hygiene Management (MHM) Kits, composed of reusable sanitary pads, underwear’s, towels, pegs, and other accessories. >1,059 vulnerable households from Kikuube (Buhuka and Kyangwali) received water buckets and aqua tabs for water purification. >2,982 female and 506 males, PSNs from vulnerable households in Kikuube and Kyegegwa received mosquito nets
Activities Outcome 1
Activity 1.1 | Conduct Training of Trainers for 15 URCS and district integrated CBHFA and ECV Facilitators
Activity 1.2 | Conduct 3 trainings of URCS volunteers on integrated CBHFA and ECV modules and selected women and child health topics
Activity 1.4 | Orient targeted community influencers (civic, religious leaders,...) on CBHFA
Activity 1.5 | URCS volunteers conduct household visits, awareness raising sessions and campaigns on CBHFA topics in targeted villages
Activity 1.8 | Organizing community dialogue sessions on CBHFA topics in targeted villages using community meetings and FGDs
Activity 1.9 | Distribution of hygiene materials to community members following a CBHFA training
Outcome 2 | Improved ability of URCS to prevent, detect and respond to disease outbreaks at the community level in the targeted districts | Total amount of people reached through awareness raising campaignes | 0 | 130000 | 0 | 86508 | 66.54% | A total of 86,508 were reahed through door to door and public awereness meeting with influencial leaders; the target of 130,000 was not attained due to the change of approach to focus more on community engagement stratey (CES) instead of mass media campaigns that had been anticipated earlier. The CES strategy more forecast on households to enhace follow up and case manegement through home based care.
Output 2.1 | URCS staff and volunteers trained and equipped to perform COVID-19 activities in targeted communities. | Number of staff and volunteers trained and equiped for COVID-19 preparedness and response | 0 | 360 | 0 | 215 | 59.72% | 215 vounteers and straff were trained as it wa deem sufficent to meetr the requiremet of the 3 districts base on the covid-19 caseloads and aslo based on the guidleines for CES instead of having the total of 360 that had earlier been planned.
Output 2.2 | URCS staff and volunteers conduct COVID-19 activities in targeted communities | Number of awareness raising campaignes organized | 0 | 36 | 0 | 24 | 66.67% | 24 awareness sessions were held with the village covid-19 task forces and URCS volunteers to raised awareness on COVID-19 and increase update of cvid-19 vaccinations. The target was not reached owing to the targeting creteria mentioned earlier exercises within the districts; risk communication; Community based disease surveillance; home based care and Psychosocial support; etc).
Activity 2.2 | Conduct branch workshop on epidemic scenario and contingency planning
Activity 2.3 | Organise and support regular coordination internal and external meetings at district levels
Activity 2.4 | *NEW*Support to surveillance systems for COVID-19
Activity 2.5 | *NEW* Integrated volunteer training (RCSM, surveillance and PSS) COVID-19
Activity 2.6 | *NEW* IEC and visibility materials COVID-19
Activity 2.7 | *NEW* Inter-personal communication and hygiene promotion at HH and community level - COVID-19
Activity 2.8 | *NEW* Crisis modifier for health emergencies - COVID 19 (relief items, food assistance or MPCT for the most vulnerable families affected by COVID-19 outbreak)
Outcome 3 | Improved resilience of communities living in high risk areas and strengthened institutional capacity of the URCS and other stakeholders to respond to HM disasters | Number of emergency committee members / members of volunteer groups in the project area showing skills in carrying relevant response tasks according to minimum standards in a coordinated manner | 0 | 450 | 0 | 450 | 100% | 45 groups of 10 members each were selected in the 45 villages in Ntoroko in the selected sub-counties of implementation. Among the 450 members were selected 220 were females and 230 were males.
Output 3.1 | Community risk management committees trained in disaster risk management. | number of trained Community Risk Management committees | 0 | 45 | 0 | 45 | 100% | The 45 groups were provided training on on Disaster Management for the Community Based Disaster Risk Reduction (CBDRR)
Output 3.2 | Communities sensitized on climate change and disaster risk reduction at community level. | Number of community sensitization sessions held | 0 | 90 | 0 | 90 | 100% | 90 session were condcucted in the communites with each community having held 2 sessions each. The sessions tackled disaster management, early warning, and sanitation promotion.
Output 3.3 | Contingency plans and evacuation routes drafted by community. | Number of contingency plans drafted, number of evacuation routes signposted | 0 | 45 | 0 | 45 | 100% | 45 sign posts with evacuation signs within each village were put in places as well as 15 community contgency plans. The project also supported the development of district contigency plan that covers the entire district including the 45 villages
Output 3.4 | Training of volunteers in DRR related topics | Amount of Red Cross volunteers trained in DRR-related topics | 0 | 50 | 0 | 50 | 100% | 50 Red Cross Actions teams were trained to EVCA and supported in the cascade in the communty CBDRR groups
Activities Outcome 3
Activity 3.1 | Organize information sessions for all stakeholders regarding the set-up of the CBDRR Groups
Activity 3.2 | Form or reactivate CBDRR Groups at village level
Activity 3.3 | Train CBDRR Groups at village level
Activity 3.4 | Organize regular CBDRR Group meetings together with the URCS volunteers
Activity 3.6 | Update, develop, procure and distribute DRR IEC materials and equipment specific to different context and target audience
Activity 3.8 | Participate in (annual) DRR awareness events
Activity 3.10 | Train BDRT (RCAT) and NDRT (National Surge Team) on VCA (Vulnerability and Capacity Assessment)
Activity 3.11 | Validate existing VCA (risk mapping) a sample of 15 communities with old risk analysis and update a district wide risk map
Activity 3.12 | Draft or update the contingency plan at community and district level
Activity 3.13 | Identify and signpost safe evacuation routes
Outcome 4 | Improved Early Warning (EW) systems at community level leading to a more targeted and effective Early Response prior to the HM disaster or thereafter | Number of community members in the project area who receive early warning messages in a timely manner from at least one source | 0 | 22500 | 0 | 28200 | 125.3% | More people reached because of increased population due to flooding events that displaced people in Kanara sub county resulting in Internally dispaced camps in the project target areas. The displacement was occassioned by rising water level on Lake Albert
Output 4.1 | Operational early warning systems are set up at community level. | Number of operational EWS that are understood by target operation | 0 | 45 | 0 | 45 | 100% | 5 stations for water level monitoring were installed and 3 community radios were provided covering the 45 villages target by the project
Output 4.2 | Community EW integrated into national/regional EW systems | Number of community EWS integrated into national/regional EWS | 0 | 45 | 0 | 45 | 100% | The 5 river guages and community radios are part of the national EWS and it covered the 45 villages and they were intergrated into the UNMA and DM systems in Ntoroko and the atioanl EWS
Output 4.3 | Assistance provided in coordination with the authorities following a natural disaster through a crisis modifier | amount of people that received in-kind/cash assistance by the project | N/A | TBD | 0 | 200 | 200 | 200 persons were provdied with NFI following flooding due to rising water levels along Lake Abert
Activities Outcome 4
Activity 4.1 | Organize Subcounty stakeholder dialogue meetings (including traditional and cultural leaders, civic leaders, religious leaders, district Meteorological department, ) to document indigenous information on early warning for floods and prolonged dry spell/drought
Activity 4.2 | Identify and validate the most adequate early-warning systems per community
Activity 4.3 | Procure and distribute early-warning tools to the selected community members
Activity 4.4 | Train RCATs and CBDRR Groups in the selected early warning systems and early actions
Activity 4.5 | Operationalize the existing MoU with Uganda National Meteorological Authority (UNMA) for dissemination of early warning messages
Activity 4.6 | Generate audience specific content from UNMA monthly forecast information and disseminate to BDRTs, CBDRR Groups and registered community members to the free U-Report sms platform
Activity 4.7 | Orient BDRT and CBDRR Groups in popularization of UNMA meteorological information and transferring it to target groups
Activity 4.8 | Develop URCS Early Warning/Early Actions Center SOPs and equip Centre accordingly for a pilot project in year 2
Activity 4.9 | Crisis modifier
Note on E7: Sigrid De Lepeleire: of 13.940 households